## 3-H
Annex 3-H
CY 2013 ODA Portfolio Review
Summary of Agency Expenditures in CY 2013
Figures in (PhP M)
Agency | Number of Projects/ Programs | Target Expenditure in 2013 |  |  |  |  | Actual Expenditure in 2013 |  |  |  |  | Actual
Expenditure in 2013
|  | LP | GP | GPH | PPP | TPC | LP | GP | GPH | PPP | TPC | (as % of target)
LBP | 3 | 0 | 0 | 796.66 | 0 | 796.66 | 800.06 | 0 | 1025.32 | 0 | 1825.38 | 229.13
ARG | 1 | 224 | 0 | 107 | 0 | 331 | 430 | 0 | 55 | 0 | 485 | 146.53
DA | 3 | 810.43 | 53.41 | 383.18 | 0 | 1247.02 | 824.32 | 84.86 | 518.54 | 0 | 1427.72 | 114.49
DOF | 1 | 12214.5 | 0 | 0 | 0 | 12214.5 | 12733.8 | 0 | 0 | 0 | 12733.8 | 104.25
DILG | 1 | 964.5 | 0 | 0 | 0 | 964.5 | 964.5 | 0 | 0 | 0 | 964.5 | 100
DSWD | 4 | 7268.83 | 0 | 1908.89 | 0 | 9177.72 | 6654.68 | 0 | 1614.59 | 0 | 8269.27 | 90.1
DTI | 1 | 46.26 | 4.21 | 12.11 | 0 | 62.58 | 33.78 | 0 | 19.61 | 0 | 53.39 | 85.32
DBP | 4 | 5372.4 | 4.42 | 1085.69 | 0 | 6462.52 | 2935.93 | 0 | 1797.9 | 0 | 4733.83 | 73.25
NIA | 5 | 2155.46 | 0 | 1314.23 | 0 | 3469.69 | 1403.37 | 0 | 1025.09 | 0 | 2428.46 | 69.99
DOE | 1 | 1089.5 | 58.4 | 106.4 | 0 | 1254.3 | 651.01 | 43.15 | 12.5 | 0 | 706.66 | 56.34
DENR | 6 | 2528.59 | 187 | 290.87 | 0 | 3006.46 | 1225.1 | 120.45 | 118.12 | 0 | 1463.66 | 48.68
BIR | 1 | 203.58 | 0 | 0 | 0 | 203.58 | 94 | 0 | 0 | 0 | 94 | 46.17
DAR | 5 | 4614.28 | 0 | 841.71 | 0 | 5455.99 | 1373.76 | 0 | 947.13 | 0 | 2320.89 | 42.54
DPWH | 15 | 10144.77 | 0 | 9548.4 | 0 | 19693.17 | 3774.61 | 0 | 4097.97 | 0 | 7872.57 | 39.98
DOH | 3 | 347.19 | 0 | 0 | 0 | 347.19 | 128.36 | 0 | 212.76 | 0 | 341.12 | 39.16
DOTC | 4 | 2379.58 | 0 | 604.87 | 0 | 2984.46 | 39.12 | 0 | 7.51 | 0 | 46.63 | 11.43
LLDA | 1 | 0 | 0 | 0 | 0 | 0 | 7.72 | 0 | 0.56 | 0 | 8.28 | NA
LWUA | 1 | 0 | 0 | 0 | 0 | 0 | 443.25 | 0 | 0 | 0 | 443.25 | NA
MWSS | 1 | 0 | 0 | 0 | 0 | 0 | 90.15 | 0 | 45.82 | 0 | 135.97 | NA
Total | 61 | 50363.87 | 307.44 | 17000.01 | 0 | 67671.33 | 34607.51 | 248.46 | 11498.42 | 0 | 46354.38 | 68.5
Notes:
1. TPC is based on revised project cost.
2. Ten projects and programs without target and actual disbursements in CY 2013 were excluded: (a) three programs and five projects that were newly effective/ signed in 2013, or were already 100% utilized in CY 2012; (b) one project that was suspended; and (c) one project with lacking/incomplete disbursement data from the agency.