## 3-O
Annex 3-O
CY 2013 ODA Portfolio Review
Projects Restructured in CY 2013
Project/IA/DP | Proposed Change/Reason | ICC Re-evaluation/ Approval Dates | Status/Remarks
Change in Scope
Loans
Agrarian Reform Infrastructure Support Project III/ DAR/JICA | Increase in the number of ARCs from 129 to 136 and reduction of target irrigable areas. The change in scope necessitated a reallocation of funds from contingencies to civil works as well as one-year extension of project completion date. | ICC: 16 Dec 2013
Puerto Princesa Airport Development Project/ DOTC/KEDCF | Change in scope to include: (a) increase in passenger terminal area from 9,492 m2 to 12,435 m2; (b) increase in cargo terminal area from 466 m2 to 1,150 m2; and, (c) addition of one apron stand (i.e., increase from the original five apron stands with an area of 20,400 m2 to six apron stands with an area of 34,000 m2). The proposed changes are based on the updated air traffic volume projections. The change in scope required loan reallocation from contingencies to building works, navigational aids and design/ consulting services. | NB: ICC-CC: ICC-TB: 3 Jun 2013
Pasig Marikina River Channel Improvement Project II/ DPWH/JICA | Additional scope – flood control structures within the Malacañang Area, and additional works and modifications to address the Presidential Security Group’s (PSG) security concerns. | NB: ICC-CC: ICC-TB: 3 Jun 2013
Pinatubo Hazard Urgent Mitigation Project III/DPWH/JICA | Additional works, such as consultancy services and construction works for Contract Packages (CP) 2, 3B, and 4. | ICC-CC: 18 Jul 2013 ICC-TB: 3 Jun 2013
Post Ondoy and Pepeng Short-Term Infrastructure Rehabilitation Project/DPWH/JICA | Inclusion of 15 additional sub-projects (8 under flood control (FC) component and 7 under roads and bridges (R&B) component). | NB: 28 Jun 2013 ICC-CC: 19 Feb 2013
Provincial Towns Water Supply and Sanitation Project III/ LWUA/KfW | Replacement of three pre-identified Water Districts with other WDs due to reluctance of the pre-identified WDs to join the project. Request also includes loan extension. | ICC-CC: 16 Dec 2013
Grants
Philippine Response to Indigenous People and Muslim Education/DepEd/AusAID | Expansion of program scope to include Region III as one of the beneficiary regions as requested by NCIP. The RDC Resolution cited a total of 236,487 IPs in Central Luzon who are entitled to have access to quality basic education | ICC Secretariat Review | Endorsed to AusAID on 6 Aug 2013 DepED has yet to account for and submit to NEDA complete reporting on all completed and planned activities vis-à-vis overall program cost
Time Extension
Loans
Second Cordillera Highland Agricultural Resource Management Project/DA/OFID | 12-month extension up to 31 July 2015 to allow more time to complete the sub-projects which were already programmed and committed by the LGUs. | ICC-TB (notation): 8 Mar 2013 | The request was already endorsed to the DOF in its letter dated 22 March 2013. On 8 May 2013, the DOF endorsed to OFID DA’s request. The OFID approved said request on 27 May 2013.
Integrated Coastal Resources Management Project/DENR/ADB, IFAD | 12-month extension to enable the completion of planned activities and maximize the benefits from the project.
Land Administration and Management Project II/DENR/WB | 6-month extension to keep the original loan effective while awaiting approval and effectivity of the additional financing as a requirement by the WB..
Provincial Towns Water Supply and Sanitation Project III/LWUA/KfW | 24-month extension up to Dec 2015 due to late start of the project because of delays in finalizing the list of water district beneficiaries, signing with DOF of the MOA on forex risk cover fee and guarantee fund, and BSP-MB final approval of the loan. | ICC-CC: 16 Dec 2013 | ICC approval is subject to a performance evaluation of the project at the end of the first year of extension through conclusion of sub-project loan agreements with water districts, submission of an action plan for the extension period with achievable targets for the next two years, among others.
Agrarian Reform Communities Project II/ DAR/OFID | 12-month extension up to 31 Dec 2014 due to difficulty of partner LGUs to comply with the NG-LGU cost sharing policy |  | Endorsed to OFID on 13 Aug 2013; concurred by OFID on 20 Aug 2013
Bridge Construction/ Replacement Project/DPWH/Spain | · Request for final extension of validity period of commercial loan (Deutsch Bank S.A.E) until final payment of EUR28,710.59 to the supplier. | ICC Secretariat Review: 23 Jul 2013 ICC Secretariat Review: 30 Oct 2013 | The validity of the commercial loan was extended until 11 September 2013. The validity of the soft loan was extended until 27 Nov 2013
· Request for final extension of validity period of soft loan (Instituto de Credito Oficial of Kingdom of Spain) until final payment of EUR83,812.19 to the supplier.
Support for Strategic Local Development and Investment Project/ LBP/WB | 13-month extension to fully finance and complete four ongoing subprojects. LBP requested DOF for 24-month extension (from 28 Feb 2014 to 28 Feb 2016) after ICC approval of the 13-month extension. | ICC-CC: 4 Oct 2013 | DOF endorsed the 24-month extension to WB on 3 Feb 2014.
Credit Line for Energy Efficiency and Climate Protection in the Philippines/LBP/KfW | 6-month extension from 30 June 2013 to 31 December 2013 to accommodate the study being done by KfW on how to move forward with the project | ICC Secretariat review : 5 June 2013
Social Welfare and Development Reform Project/DSWD/WB | 18-month extension from 30 June 2014 to 31 December 2015 to cover more beneficiaries/grant recipients under the 4Ps | DBCC approved
Philippine Energy Efficiency Project/ DOE/ADB | 6-month extension from 30 June 2013 to 31 December 2013 to complete the commissioning of the Lamp Waste Management Facility
Grants
School Building Program for Basic Education/DepEd/ AusAID | 10-month extension from 30 August 2013 to 30 June 2014 due to delayed project start. Further, the national and local elections in May 2013 affected the local bidding process. | ICC Secretariat Review | Endorsed to AusAID on 4 Nov 2013
Support to the Philippine Basic Education Reforms/DepEd/WB | 6-month extension from 31 May 2013 to 30 Nov 2013 to make-up for delays in the construction of classrooms and procurement of equipment necessary to operationalize the Learning Resource Management and Development Centers. | ICC Secretariat Review | Endorsed to WB on 22 May 2013; approved by WB on 31 May 2013
Education Performance Incentive Partnership/DepEd/AusAID | 12-month extension from 31 December 2013 to 31 December 2014. Problem with project design (i.e., project is an incentive program and should not require expiration to allow for flexibility in disbursement based on DepED priority
Change in Cost
Pasig Marikina River Channel Improvement Project II/ DPWH/JICA | Increase in project cost by PhP932.83 million (from PhP4,608.68 M to PhP5,541.51 M) to fund the additional scope discussed in Projects with Change in Scope. | NB: 26 Jun 2013 ICC-CC: 19 Feb 2013 ICC-TB: 21 Nov 2012
Pinatubo Hazard Urgent Mitigation Project III/DPWH/JICA | Additional cost of PhP463.588 million (from PhP5,285.67 M to PhP5,749.26 M) to defray additional expenditures from the requested additional works. | ICC-CC: 18 Jul 2013 ICC-TB: 3 Jun 2013