## 3-P
Annex 3-P
CY 2013 ODA Portfolio Review
Projects with Loan Cancellations/Other forms of Restructuring
Project/IA/DP | Proposed Change/Reason | ICC Re-evaluation/ Approval Dates | Status/Remarks
Cancellation
Loans
Credit for Better Health Care Project/DBP/ADB | Cancellation of US$10.88 million (PhP500 M) as a result of the dropping of possible Metro Manila projects | NB: 21 Nov 2013 ICC-CC: 5 Aug 2013 | Cancellation endorsed by DOF to ADB on 12 Feb 2014
Integrated Coastal Resources Management Project/DENR/ADB, IFAD | US$7.41 million was cancelled representing uncommitted loan balances from (a) Component D-Civil Works (US$3.14 million) and (b) Interest and Commitment Charges (US$4.27 million) which cannot be utilized by loan closing date of June 2014.
Others (Reallocation of Contingencies, Extension of Physical Completion Date, etc.)
Loans
Agrarian Reform Infrastructure Support Project III/DAR/JICA | A reallocation of funds from contingencies to civil works and 12-month extension of project completion date resulted from the change in scope | ICC: 16 Dec 2013
Integrated Coastal Resources Management Project/DENR/ADB, IFAD | A reallocation of US$1.14 million was done (US$0.71 million from different categories and US$0.43 million from the unallocated fund) to (a) Resource Management and (b) Dissemination, Demonstration Trials categories which exceeded the original allocations by US$0.51 million and US$0.63 million, respectively.
Philippine Port and Coast Guard Capacity Development Project/DOTC-PCG/ France | The project was proposed to utilize the remaining loan of the cancelled GMA Ports Project in parallel with request for one-year loan extension from November 2013 to November 2014 | NB: Nov 2013 Joint ICC-TB and CC: 8 Apr 2013 | NB approval was with the condition that DOTC-PCG shall submit an acceptable unit cost comparison for the 82-m patrol boat to be procured. DOTC has submitted pertinent documents to OP for decision.
Puerto Princesa Airport Development Project/ DOTC/KEDCF | Loan reallocation from contingencies to building works, navigational aids and design/ consulting services ensued from the change in scope. | NB: ICC-CC: ICC-TB: 3 Jun 2013
Pasig Marikina River Channel Improvement Project II/ DPWH/JICA | Reallocation of loan proceeds amounting to JP¥234,379,617 from the Consulting Service and Contingency Components to the Civil Works Component. Said reallocation was necessitated by the approved increase in project cost. | NB: 26 Jun 2013 ICC-CC: 19 Feb 2013
Post Ondoy and Pepeng Short-Term Infrastructure Rehabilitation Project/DPWH/JICA | Reallocation of PhP461.20 million from the projected loan savings of the FC component and equivalent replacement amount for the rendered excluded and/or ineligible sub-projects under R&B component. Said reallocated funds will be used for the proposed additional 15 sub-projects. | NB: 28 Jun 2013 ICC-CC: 19 Feb 2013
Social Welfare and Development Reform Project/DSWD/WB | Reallocation of US$1.5 million to the Goods, Training, Consultants, and Incremental Operating Costs Category | DBCC approved
Philippine Energy Efficiency Project/DOE/ADB | Reallocation of loan proceeds as a result of change in scope