## 3-Q
Annex 3-Q
CY 2013 ODA Portfolio Review
Projects Likely to be Restructured in CY 2014
Project | Reasons for Restructuring
DPWH
Gapan-San Fernando-Olongapo Road Project II (GSO II) | One year loan extension to cover payments of outstanding claims to cover the civil works contract post-construction activities of GSO II.
Bacolod-Silay Airport Access Road Project (BSAARP) | One year loan extension and reallocation of loan balance for the detailed engineering design (DED) of the proposed second phased of the project.
Road Upgrading and Preservation Project (RUPP) | Change in scope for the reconstruction/ replacement of nine earthquake-damaged bridges in Bohol
Road Improvement and Institutional Development Project (RIIDP) | Changes in scope for the reconstruction/ replacement of earthquake-damaged works; likely to increase in cost due to change in scope
Mega Bridges for Urban and Rural Development (MBURD) | Change in scope for the reconstruction/ replacement of three earthquake-damaged bridges in Bohol
Mindanao Roads Improvement Project (MRIP) | Request for re-availment of the loan to fund the proposed additional project scope.
DOTC
Laguindingan Airport Air Navigation System and Support Facilities Supply Project (ANSSF) | Potential candidate for loan extension in view of implementation delays. (Request for 18-month loan extension received by NEDA on 21 February 2014)
New Communications, Navigation and Surveillance/Air Traffic Management (CNS/ATM) Systems Development Project | Change in scope, specifically the addition of three controller work stations, depending on the results of an updated air traffic study to determine the need for such
Philippine Port and Coast Guard Capacity Development Project (PPCGCDP) | Request for loan extension due to significant time spent in securing government’s full approval of the project
LBP
Credit Line for Energy Efficiency and Climate Protection in the Philippines (CLEECP) | No takers (relending project) which will lead to changes in scope to utilize the loan
DA
Second Cordillera Highland Agricultural Resource Management Project (CHARMP2) | Delay in the availability of agency’s Counterpart Financing Assistance (CFA)
LLDA
WB-AF assisted Laguna de Bay Institutional Strengthening and Community Participation Project (LISCOP) | Cancellation due to change in priorities and change in administration
NIA
Participatory Irrigation Development Project PIDP | Loan extension as well as reallocation of loan proceeds due to significant delays brought about by prolonged procurement of civil works contracts. NIA also reported that the delays encountered were also due to activities related to the implementation of the agency’s Rationalization Plan