## 4-A
Annex 4-A
CY 2013 ODA Portfolio Review
Findings and Recommendations in Supervision Missions
Agency |  | Project | DP | Mission | Date | Rating/Findings | Recommendations/ Remarks
1 | NIA | PIDP | WB | Implementation Support | 29 Apr-10 Jun
2 | NIA | PIDP | WB | Implementation Support | 4-15 Nov
3 | DSWD | SWDRP | WB | Implementation Support | Jun | Satisfactory
4 | DSWD | SPSP | ADB | Midterm Review | Aug-Sept | Highly Satisfactory | - Reaffirmed continued progress made under the 4Ps and NHTS-PR - While the 4Ps targeted to cover 1 million HHs under the 4Ps, this has expended to actually cover 3.9 million - Reaffirmed continued relevance of SPSP’s design and monitoring framework (DMF) and directly supports the GPH’s social protection reform program
5 | DA | RaFPEP | IFAD | Midterm Review | 16 Sept-02 Oct | Satisfactory. The overall assessment of the sub-program’s implementation and likelihood of achieving the project objectives were both rated satisfactory. | In order to increase the likelihood of achieving the sub-program’s activities, the Mission team recommended the project to focus on the following activities: (a) completion of the Irrigator’s Associations Strengthening process; (b) investing the remaining funds from the IFAD loan to further improve the target communal irrigation systems in Regions VI, VIII and X; (c) continue with the buffer stocking of certified seeds for paddy as safeguard against natural calamities; (d) mainstream the farmer field school extension approach as a regular extension approach; (e) start reporting on outcome indicators as stated in the logical framework; (f) for the government of the Philippines to countersign the amendment to the Financing Agreement as soon as possible. The Financing Agreement was sent to the DOF on 2 April 2013 for countersigning. DA is still awaiting response from the DOF.
6 | DA | CHARMP2 | IFAD | Supervision Implementation Support | 03-18 Feb | The Mission team found that progress has been slow as confirmed by the recorded low utilization of funds, and both negative physical and financial slippages. The likelihood of achieving the project’s objectives is put at risk since implementation of critical agreed actions during the Mid-Term Review mission have yet to be completed. | It is recommended by the team to urgently address the decentralization issue, which caused delays in CY 2012, to avoid bottlenecks at the Project Steering Office.
7 | DENR | NPSENRMP | WB | Implementation Review | 17-28 Jun
8 | DENR | NPSENRMP | WB | Implementation Review | 03-13 Dec
9 | DENR | ICRMP | ADB | Loan and Grant Review | 19 Mar- 3 Apr
10 | DENR | ICRMP | ADB | Loan and Grant Review | 21-29 Oct 2013
11 | DENR | IPOPMP | WB | Implementation Support | 05-16 Aug
12 | DENR | MTSP | WB | Implementation Support | 23-31 Jan
13 | DENR | MTSP | WB | Implementation Support | 21-24 Oct
14 | DENR | PCEEP | WB | Project Implementation Reiew | 11-15 Feb
15 | DENR | PCEEP | WB | Project Implementation Review | 23-30 Jul
16 | DENR | PhilCCAP | WB | Interim Technical Review | 02-10 May
17 | DENR | PhilCCAP | WB | Implementation Review | 03-13 Dec
18 | DAR | ARCP2 | ADB/ OFID | Joint Loan Review | 12-17 Sept | Behind schedule. - Project progress, especially on disbursements of civil works, was behind schedule mainly due to: (i) limited capacity of participating LGUs in financial management and fund disbursement; (ii) lengthy procedures for subproject approval and implementation process; and (iii) changes in local leaderships and DAR ARMM authorities following the national and local elections. - The Mission expressed its concern on the low utilization of the OFID loan and insisted ARMM to channel its efforts to focus on strategic measures that would be required to improve the fund disbursement and utilization keeping the loan closing date in mind. - The Mission believes that Project progress is acceptable but needs to expedite its implementation. The CDD, AED, and PM related activities were generally implemented as planned. However, progress in RI sub-project implementation and disbursement needs to further expedite. - The Mission believes that the DAR ARMM and NPCO will be able to make more significant progress before the end of 2013. | - The Mission recommended a mid-term review mission in early February 2014 to review the project design, scope and implementation arrangement. - The following are some of the key recommendation to prepare the mid-term review that can be scheduled in February 2014 by (i) formulating the TORs of the special task force for the overall project management in ARMM by 31 December 2013; (ii) preparing a project results profile by 31 December 2013; and (iii) preparing options for the Project to reallocate the loan proceeds.
19 | DPWH | NRIMP II | WB | Implementation Support | 30 Sept-09 Oct | - Based on the assessment, good progress has been made for all components toward the achievement of the project development objective. - The Road Improvement component will complete all activities by closing date in December 2014. The mission confirms the substantial savings from the competitive process. - The Preventive Maintenance component has five completed contracts under the first year program and seven contracts are ongoing under the 1st and 2nd year programs. The DED consultant is on board for the 3rd and 4th year programs. - The Institutional and Capacity Development (ICD) component is now being implemented smoothly after a slow start-up and has 17 out of 18 goods and consultancy contracts ongoing. - The disbursement rate is still low but does not reflect the physical accomplishment which is much higher. The project is proposed for restructuring in order to reflect the reality on the ground and the implementation delays.