## 4-B
Annex 4-B
CY 2013 ODA PORTFOLIO REVIEW
Disaggregated Lessons Learned CY 2013 ODA
Sector | Pre-Project Implementation | Budget- Related and Funds Flow | Project Management | LGU-Related
Agriculture, Agrarian Reform and Natural Resources (AARNR) | 1. Proper scheduling of component implementation in project design – For projects with multiple components proper scheduling of the start of implementation of components is critical to ensure timely implementation of components, especially for components which are dependent on the completion of another component. In the case of CHARMP2, the start of implementation of the rural infrastructure development component was made the same with the other four components. As a result, activities of the RID component were delayed since it should have only commenced when all the necessary preparations and enabling environment were already put in place by the other components. (DA) |  | 1. Effectiveness of proclamation/ advocacy campaigns. - In spite of the typhoons and calamities that hit the country during the second half of the year, total palay production reached 18.44 million MT in CY 2013, which is 97 percent of the rice production target of 20.04 million MT. Although three percent short of the 100 percent target, this is considered the highest rice production recorded in the last 30 years. The NYR 2013 proclamation appeared to be effective in bringing efforts of various stakeholders i.e., farmers’ groups, LGUs and the private sector together, thus boosting up rice production for the year. Similar proclamations and advocacy campaigns may also be used to enhance production for other agricultural products. (DA) | 1. Timely provision of counterpart fund - The delayed provision of LGU counterpart funds has been a primary factor in the delayed implementation of rural infrastructure subprojects. In the case of Antique province in Region VI, implementation of rehabilitation activities was on track due to the timely provision of LGU counterpart fund from the provincial and municipal governments. (DA)
| 2. Assessment of agency absorptive capacity and risk factors - The agency should gauge its capacity to take on additional projects, and account risk factors i.e., timing, delay in loan effectiveness, before engaging in other projects to be co-implemented with other IAs to avoid subsequent cancellation of loans, delaying start-up activities of the other project. (DA) |  | 2. Tapping local contractors for simple works - Simple rehabilitation works such as the construction of concrete canals and small contracts amounting to around PhP1.5 million can be implemented quickly (two months) and for which many local contractors are qualified. (DA) | 2. Omnibus NCIP Certification for LGU - LGUs have difficulty in complying with the requirement for an NCIP Certification for proposed sub-projects. To facilitate issuance of NCIP Certification, DAR requested the NCIP Head Office for an omnibus clearance for subprojects in areas where there are no ancestral domains. (DAR)
| 3. Early set-up of PMO and adequate personnel complement - Delayed set-up and inadequate personnel are recurring issues that have caused delays in project implementation e.g. PIDP and NISRIP. Succeeding projects should strive to be proactive in preparation (establishment of PMO, detailed engineering and design, etc.) prior to loan signing and aim for sufficient qualified personnel to jumpstart projects from the outset/startup stage. It is noted that ARIIP is one project with adequate personnel, which have contributed to its good project performance. (NIA) |  | 3. Close coordination with the contractors - Regular coordination meetings were conducted by the Project Management Office with the project contractors. (DA) | 3. Social preparation - Projects involving LGUs, behavioral changes and institutional strengthening take time. Also dynamics between NG and LGU could cause delays in said projects e.g. securing clearances from NG, complying with NG policies etc. Lastly, changes in leadership in LGUs could have an impact on the continuation of a sub-project. These factors need to be examined and considered by the LLDA in design of similar projects in the future, to avoid pitfalls encountered in LISCOP. (LLDA)
|  |  | 4. O&M Training for Sustainability - For RaFPEP, on the sustainability of the rehabilitated and restored CIS, it was observed that focus of the IA strengthening activities were more on the planning and implementation phase of the systems. It is critical for Irrigator’s Associations (IAs), especially those with minimal experience in operating such systems, to be well-trained and capacitated on O&M, i.e., collection of Irrigation Service Fee that will finance the O&M activities (DA) | 4. Enabling LGUs - Strengthening the capacities of LGUs to plan and prepare sub-project proposals generated interests of local executives to avail of the facility under LISCOP, and also led to the implementation of other projects in the Laguna Lake area. Continuity of such capacity can be ensured by providing training to LGU employees with permanent appointments, not those on co-terminus appointments with the local chief executives. (LLDA)
5. Scheduling of implementation - A big implementation challenge in terms of funds flow and project execution is the absence of a Philippine Country Office (OFID, BNP Paribas) for the development partner/ funding institution as well as collaboration efforts between the executing agency and the implementing agency. To ensure that outputs and outcomes are delivered as scheduled, delays realized during ongoing project’s must be imputed into future projects’ timelines. (DAR)
6. Synchronized planning and budgeting project activities would ensure timely execution of activities avoiding delays in the process. (DENR)
7. Top Management supervsion of projects, including close monitoring of project (i.e; weekly reporting to ExeCom) as well as proactive roles of bureaus/implemeting units improve project performance. (DENR)
8. The integration of project activities to the regular functions/operations ofthe agency for purposes of ownership would ensure sustainability of project outputs. (DENR)
9. Post-Rationalization Plan-The NIA Rat Plan targeted within a five-year period (2008-2012) and aimed to minimize overlapping/duplicating functions, and improve on the agency’s systems and procedures. On the other hand, the implementation of the Rat Plan has contributed to delayed implementation in its projects, particularly PIDP which encountered delayed procurement of big-ticket civil works contracts. NIA needs to prepare its Post-Rationalization Plan to further improve its business processes and should draw on lessons learned from its implementation, to determine what more interventions are relevant for the agency. (NIA)
10. The ARIIP experience- The ARIIP was one of seven nominees in the past Good Practice Awards (Strategies in Resolving Issues in Project Implementation). It was the only project that was consistently on-schedule in NIA’s ODA Portfolio. NIA should take into account ARIIP’s strategies to address funding, environmental and social constraints: (a) reducing the project cost due to modifications in structural alignment (construction of left bank protection dike and re-regulating pond); (b) reducing siltation and re-regulating pond serving as catchment basin for heavy rains and overflowing water from San Roque Dam; and, (c) reducing the risk of the neighbouring communities because of the realigned structures, and assess applicability of crafting Modified Revised Plans suitable to actual field conditions to future projects. (NIA)
Governance and Institutions Development (GID) | 1. Preparatory activities – It is critical to project implementation if the commitment of involved stakeholders should be secured at the outset prior to actually implementing a project. This is in order to avoid delays and more importantly, assure a project’s sustainability and long-term relevance. (SC) |  | 1. Skill-level/capacity of personnel - Efforts to enhance current capacities and meet the skill-level required by a new IT system are desirable is necessary for sustainability of the system. (SC)
2. Project sustainability – Equipment and spare parts of a specific information/data system poses sustainability-related challenges if there is a local shortage. Events like disasters or human error adversely affecting the structure can cause significant work disruptions if spare parts or equipment are not readily-available locally. (SC)
Transportation | 1. Thorough Feasibility Studies - On LADP, a deeper assessment of the merits of the early operation of the airport should have been conducted. As it is, air transport passenger safety is a continuing concern and there is need to revise the implementation schedule of the necessary air navigation system due to working time limitation. (DOTC) |  | 1. Capacity improvement of DPWH ROW personnel is crucial to support the implementation of national priority projects. Successful implementation of the RROW undertaking in line with RAP depends on the quality of human resources and their capability in performing the tasks and assignments. (DPWH)
| On PPADP, thorough investigation and provision of an updated air traffic volume projection to decision-makers early on is crucial in order to come up with the appropriate airport design. (DOTC) |  | 2. Prolonged decision-making - At certain instances, the agency has flip-flopped or adopted a "wait- and-see" attitude when deciding on whether to continue an ODA project under ODA financing or completely shift to local financing. Whatever the context and intention was, it has cost the agency valuable time that is likely to result in delayed realization of project benefits. (DPWH)
3. The approach of DPWH towards institutionalizing an agency-wide results monitoring system, through a WB grant project is highly commendable. (DPWH)
7. On LRT I Capacity Expansion II:
due to low levels fixed fares, LRTA’s net operating profit has been in chronic deficit and it would continue to be in deficit if there will be no revision of fares. Furthermore, there are currently many uncertainties regarding the concession contract for O&M of Line 1, and there is a need for the government to follow up and process smoothly the concession. (DOTC)
On the spare parts concern, the LRTA is faced with difficulties to procure parts for second generation rolling stocks. While first and second generation rolling stocks are planned to be phased out and fourth generation rolling stocks are planned to be procured, there is a need to consider the specification of spare parts when preparing bidding documents for fourth generation rolling stocks, so that the use of spare parts could be maximized in the third and fourth generation rolling stocks resulting in high operating rate of rolling stocks. (DOTC)
Industry, Trade and Tourism (ITT) | 1. Focus on geographical area, income classification on the other hand made the program limiting as the other program funds are demand driven. There have been instances where prioritization has to be established to meet the program conditions. (LBP) | 1. Fixed interest rates and longer repayment terms support most of the infrastructure projects of LGUs. This allowed cash flow and budgeting of the LGUs’ limited funds easier. (LBP) | 1. Project implementation in remote areas such as Tawi-Tawi is more challenging in terms of project supervision and monitoring due to the distance as compared with LGUs located in the main island of Mindanao. Almost all projects in Mindanao have certain levels of risks. (LBP)
2. Use of GPH procurement guidelines - Procurement guidelines, documents and requirements of the program follow the existing LBP guidelines (RA 9184), thus, most of the LGUs who participated are already familiar with the documentation. LIP was also much easier to market to LGUs because of the wider range of eligible projects; (LBP)
Social Reform and Community Development (SRCD) | 1. Instituting Effective M&E Mechanisms -The Regional M&E Plan and Adjustment (RMEPA) Meeting, one of the technologies introduced by PRIME, is an efficient platform where Division DepEd officials and those on the ground can share their major accomplishments, lessons learned and issues to the Regional DepEd officials. As what was observed during the MES project monitoring visit at the Region XII RMEPA, division superintendents, M&E focal persons and other DepEd officials actively shared their experiences which provided a wealth of information on the best practices which other Divisions can adopt. The needed technical assistance of the participating Divisions from the DepEd Regional Office (DRO) was also discussed, thus providing a plan of action where the RDO can intervene. (DepEd) | 1. Program Loans vs. Project Loans - While most of the grants are contracted/ managed by other entities, this should not delimit the role of DepEd as the owner of the programs/project. The participation of DepEd in the various phases of implementation (even during the approval phase) provides an added value to the grants, making DepEd not just a recipient but as a partner and an active player in delivering the results of the ODA program/ project. Moving forward, the need to track the contribution of various assistance towards achieving DepEd’s objectives is an essential exercise that must be conducted with prudence by the DepEd - PDED. (DepEd) | 1. Strengthening ownership of ODA Programs and Projects. - NEDA faced difficulty in monitoring accomplishment of the program support. NPSBE’s direct contribution to the achievement of the reported output and outcomes is difficult to determine since program loans are diffused within the agency’s budget. NPSBE (as in other NPS) adopted the national targets which were deemed too ambitious for a single project. While DepEd reports considerable accomplishments in terms of achieving the national targets, a caveat exists in directly attributing these to the NPSBE. NPSBE at this point is treated as a contributory agent in the achievement of the reported accomplishments. (DepEd) | 1. Database for Identifying the Poor – A reliable database such as the NHTS-PR is important for other government units in identifying beneficiaries and properly designing development projects. (DSWD)
| 2. Preparatory activities – To avoid start-up delays, it is important to include in the list of start-up activities a briefing or coaching of financial management personnel to narrow the familiarity gaps regarding budget policies. (DSWD) |  | 2. M&E Scorecard -(Good Practice: BEAM – ARMM) Other programs, especially those with various components may develop an M&E scorecard. This provides a quick overview of project/program performance allowing one to easily identify problem areas and expedite the decision making process. The M&E scorecard may likewise increase other stakeholder’s appreciation of the monitoring processes. (DepEd)
| 3. Conduct of demographic analysis, KAP study, and gap analysis early on - Often, development actors focus on the technical aspects of the project and also on achieving results and give little time and effort in knowing the people who are supposed to be the center of their development efforts. Disregard of people’s knowledge and perceptions often lead to poor cooperation during implementation and poor utilization of facilities upon completion – problems which could have been avoided had people been involved in the project from the start. Apart from gaining a deeper understanding of the beneficiaries, the analyses and studies conducted by NCIP are expected to help refine its interventions for the purposes of the project. (NCIP) |  | 3. Convergence of Social Protection Projects/Programs - Co-implementation of Community-Driven Development (CDD) projects and 4Ps in a particular area has the potential to further enhance general welfare, since beneficiaries are better able to benefit from more accessible social infrastructures (e.g. roads, schools, day-care centers, health centers, etc.), improve their health and educational status, and at the same time receive financial grants from the Government. (DSWD)
4. Quick Response Mechanism A quick-response mechanism in the aftermath of natural calamities is critical in ensuring the sustainability of completed outputs/structures from a project. (DSWD)
Water Resources | 1. Longer implementation period for large scale water supply project proposals involving WDs as beneficiaries cannot be implemented in just two years from loan effectivity. The project implementers would need at least a year more to prepare the WDs to implement their respective subproject proposals. The extra time provided would enable them to address the regulatory bottlenecks as well as the project launchings, economic-financial evaluation of the WDs subproject proposals, signing of sub-loan agreements, procurement, etc. (LWUA) | 2. Support from Private Enterprises Concessionaires) – Profit-motivated involvement of MWCI and MWSI with the MWSS operations provided an opportunity for more physical investments and at the same time contributed to a project’s timely and efficient implementation, as these enterprises’ business operations could be adversely affected by a poorly-implemented or a non-performing project. (MWSS) | 1. ROW – Adherence to the UDHA guidelines have proven to be an effective means of carrying out ROW activities. Under the UDHA guidelines, an adequate disturbance compensation for affected families is an alternative option to relocation. (MWSS)
2. Project Management – A proactive and well-coordinated project management team that encompasses all stakeholders including the CO, MWSS top management, concessionaires, consultants and contractors, and LGUs should complement or suit a project’s specific construction methodologies. (MWSS)
3. Competitive lending rates - LWUA has to make its relending terms for water supply development loans be competitive with other financing rates in the sector. With the availability of low interest loans being offered to water districts by other government and private financing institutions and the provision of grant funds by the Government to water districts, the higher-interest LWUA loan facilities become less preferred by WDs. (LWUA)
4. Changes in leadership/PMO staff - Frequent changes in the organization may also affect project implementation. From the time the project was proposed, there have been three instances of change of leadership and transfer of personnel of LWUA. In addition, many government personnel also opted to retire due to the government reorganization/streamlining program. The change and reduction of personnel especially those involved in the project have in some ways affected its implementation. (LWUA)