## 4-C
Annex 4-C
CY 2013 ODA Portfolio Review
Lessons Learned from Completed Projects
Project Title | IA | DP
Lessons Learned
1. Kapit-Bisig Laban Sa Kahirapan-Comprehensive and Integrated Delivery of Social Services (KALAHI-CIDSS) | DSWD | WB | · CDD approach enhances the effectiveness of the local poverty reduction initiatives as barangay action plans that were prepared by communities serve as inputs to the local poverty reduction action plan of the LGU. Further, the Municipal Inter-agency Committees (MIaC), which were instituted under the KALAHI-CIDSS, enhanced local coordination and multi-sectoral approach to local development. Through the MIaC, the municipal staffs are now more engaged and more aware of the needs of far-flung communities.
· Community oversight helps ensure smooth sub-project implementation while community participation lowers cost and improves construction quality of sub-project investments-- with cost differences ranging from 8 percent for schools and 30 percent for water supply. Further, community contributions (cash and in kind), foregone wages and local materials help lower costs and promote greater ownership
· LGU support is important particularly for sustainability. Some LGUs have institutionalized KALAHI-CIDSSS through: (a) passage of municipal resolutions in support of CDD approaches; (b) hiring previous KALAHI-CIDSS staff as municipal employees; and, (c) innovative funding mechanisms to support community priorities. From such emerged the Makamasang Tugon or LGU-led implementation under the KC-AF wherein LGUs take the lead role in local CDD implementation (with DSWD as support). Hence, further lessons should be extracted in the KC-AF.
· Community facilitators, being the frontline staff, are crucial to the success of sub-projects, hence the importance of sufficient training.
· The project enhanced local resource mobilization efforts as some LGUs and communities secured supplemental contributions from private and public sources such as Priority Development Assistance Fund (PDAF) of congressmen, provincial government, NGOs, etc. This was also observed in some cases when the sub-projects identified by communities were not prioritized.
2. Second Agrarian Reform Communities Development Project, Phase II (ARCDP II) | DAR | WB | · The new cost-sharing scheme applied (from 10%-30% under ARCDPI to 50%-100% of the total cost of infrastructure subprojects) increased the equity share of participating LGUs. The new cost-sharing scheme was too high for most lower-income LGUs and it became difficult for the LGUs/ARCs to provide the required equity within the time period. The revised NG-LGU cost-sharing policy should be pilot-tested prior to its formal adoption and institutionalization by the concerned implementing agencies.
· The funding constraints were mitigated by DAR providing “bridge-funds” to the project and the approval of the AF, thus allowing the project to pay its obligations to contractors and suppliers. The establishment of a revolving bridge-financing as a stop-gap measure for cash flow-related issues could be considered in other projects where the MDFO processing remains to be a setback.
· Coordinated support and complementation of resources proved effective in facilitating the critical and connected interventions that generated greater benefits and outcomes. ARCs receiving this kind of support from a range of stakeholders demonstrated more organizational ability to generate economic and social benefits from various investments. Regular and frequent consultations with project stakeholders resulted in timely resolution of project-related issues
· Starter kits, which were provided to an initial group of training participants, were recognized as an effective strategy in ensuring the adoption of training inputs. The recipients were then required to pay these in-cash or in-kind, and the repayments were distributed to the next-in line training participants in the form of loans and the cycle goes on. This is known as the Agriculture and Enterprise Development (AED) “Roll-Over” Scheme. The Project also facilitated links between ARC cooperatives/organizations and microfinance institutions. Under the Micro Finance Solutions (MICROSOL) Project and Agri-Finance Solutions (AGRISOL) Project, 100 ARC cooperatives (133% of the target) were able to access credit, hence, benefitting 39,079 clients (102% of the target). The Microfinance Innovations in Cooperatives (MICOOP) Program introduced in the latter stage of the project showed increased access to loans by the cooperatives. Adoption of strategies such as roll-over investment schemes, expanded role of the Barangay Implementing Team (BIT) and the innovative financial service programs maximized the spread of benefits to more ARC households.
· Development interventions should be holistic and integrated to be effective in achieving its objectives. Investments in capacity building and skills development of target beneficiaries, technical and financial assistance for livelihood and income enhancement, and infrastructure development.
3. Arterial Roads Bypass Project, Phase I (ARBP I) | DPWH | JICA | · Value of Resettlement Action Plan (RAP). The preparation of Resettlement Action Plan (RAP) is an important step in ascertaining the project impact, foremost its impact on socio-economic and cultural life of the people. The process of preparation of RAP provides a venue for the people in the community and other stakeholders and the DPWH to have a dialogue and resolve issues arising from ROWA.
· Need for capability building of DPWH personnel. Improving the capability of DPWH ROW personnel is an urgent concern to support the implementation of national priority projects. Successful implementation of the RROW undertaking in line with RAP depends on the quality of human resources and their capability in performing the tasks and assignments.
· Implementation was hampered by various types of delays such as right-of-way acquisition, financing concerns, review/evaluation/approval of design schemes, change in scope, procurement, etc. Based on project performance, it appears on hindsight that the proponent had underestimated these attendant risks. Resulting time extensions could have been avoided through improved project planning.
· Value Analysis in the project development cycle (i.e., conceptual stage, feasibility stage and/or implementation stage) is an important means to ensure project’s quality, performance and functionality while minimizing construction, operation and maintenance costs.
· For projects in which completion of some activities go beyond the loan closing, options other than loan extension should be explored. Among these options are use of local funds and advance payment/disbursement for the completion of remaining activities with the posting of performance bond/securities.
4. Local Government Units Investment Programmes I and II (LIP I & II) | LBP | KFW | · Project implementation in remote areas such as Tawi-Tawi is more challenging in terms of project supervision and monitoring due to the distance as compared with LGUs located in the main island of Mindanao. Almost all projects in Mindanao have certain levels of risks;
· Procurement guidelines, documents and requirements of the program follow the existing LBP guidelines (RA 9184), thus, most of the LGUs who participated are already familiar with the documentation. LIP was also much easier to market to LGUs because of the wider range of eligible projects;
· Fixed interest rates and longer repayment terms support most of the infrastructure projects of LGUs. This allowed cash flow and budgeting of the LGUs’ limited funds easier;
· Focus on geographical area, income classification on the other hand made the program limiting as the other program funds are demand driven. There have been instances where prioritization has to be established to meet the program conditions; and,
· The program limits the loanable amount per LGU. Most of the LGU loan applications belong to higher income classification and thus have several projects lined-up for implementation. Given the set loan amount limit, other projects of LGUs have shifted to other program funds.
5.National Program Support For Basic Education (NPSBE) | DepED | WB | · National Program Support. While the NPSBE only accounts for a relatively small proportion of the overall DepEd budget, it was critical in leveraging additional resources and in mobilizing other resources from development partners as well as the local private sector – partners assistance in moving BESRA forward.
· The institutionalization and the subsequent utilization of the eNGAs would address problems in financial reporting.
· While SBM already made significant progress, some schools, still need to strengthen roles of the school governing councils as well as in increasing community participation.
· NEDA – MES had very limited information during its appraisal stage rendering it difficult to assess Program’s intended targets at appraisal and the actual Program accomplishments
· NPSBE’s direct contribution to the achievement of the reported outputs and outcomes is difficult to determine since program loans are diffused within the agency’s budget.
· NPSBE at this point is treated as a contributory agent in the achievement of the reported accomplishments.
· Solid analytical studies on system reforms were also critical in ensuring smooth implementations of the program.
6. Southern Philippines Irrigation Sector Project (SPISP) | NIA | ADB | · Participation of beneficiaries at an early stage of subproject preparation will enhance the chance of success where beneficiaries are to assume control of O&M.
· Beneficiary contribution must be set at a level that reflects their capacity to pay, and it is considered inappropriate to overload farmers with higher costs where poverty remains an issue.
· Quality sub project feasibility and detailed engineering designs, based on solid geological and topographic surveys, are necessary prerequisites to successful irrigation and road subprojects. Without these, unachievable targets will be established that cause subprojects to be assessed less successful.
· The role of the local government units must be understood, given their limited resources and their primary function as a political institution. While they remain an important inclusion from a lobbying perspective, they cannot adopt roles beyond the level of which they have human and financial resource capacity.
· Further capacity building must be undertaken in procurement and bid evaluation if provincial and regional procurement is to be continued in similar future projects. While there is certain autonomy in regional centers, the central government and ADB should adopt a stronger procurement monitoring role, if only to prevent repetition of previous mistakes.
· A realistic evaluation of institutional capacities is needed during project preparation for the tasks expected of them. This is particularly important with the proposed downsizing of the NIA that is currently taking place.
· Stronger links with technical support and input supplies such as credit should be part of the training of IAs during subproject implementation. While attempts at coordinating technical support were envisaged, much of this came down to personal relationships, and that varied widely between subprojects.
7. Judicial Reform Support Project (JRSP) | SC | WB | · As issues and concerns are complex, they may be addressed through various approaches, thus, the lessons learned listed which are stemming from a common issue or concern, are interrelated.
· There should therefore be a mechanism for SC to establish PMOs/project staff even before project/loan effectiveness date.
· There should be effort however, towards the sustainability/institutionalization of the technology transferred.
· The practice would have encouraged early adoption and smoothen transition during the institutionalization phase of project interventions.
· As was prescribed under RA9183 for the government-wide procurement, so should the SC prescribe internal guidelines for strict compliance to contain delays.
· There should have been early identification and F/S activities of pilot areas such that said activity should have been undertaken before loan effectiveness.
· It should be noted however, despite the efforts that there were factors beyond the control of the JRSP that ultimately led to the downsizing of the project scope.
· should have an advocacy program for new administrations to keep ongoing projects within the leader’s priority concerns and keep them abreast with the pace of project implementation.
· The SC has therefore in its portfolio a number of ODA as well as locally funded projects that target specific judicial reform areas.
8. National Program Support For Tax Administration Reform (NPSTAR) | DOF/BIR | WB | · The BIR portfolio being heavy on IT/automation components is bound to experience time overruns. The Standish Group’s Chaos Report for 2002 states that 51 percent of IT projects are completed with cost and time overruns.[1] The most cited reason for failures in IT projects have been incomplete and changing requirements and lack of user involvement. As with the NPSTAR, challenges were mainly due to changes/additional requirements by the BIR that are not covered under the existing goods or consulting services contracts. In addition, the project is also instituting systemic reforms that would require cultural changes within the BIR including the adoption of specific performance/accountability indicators. Given these, the BIR could have minimized delays and overruns had there been clearer statement of requirements, more and early user involvement and open and clear communication lines among the stakeholders.
9. ARMM Social Fund (ASF) | ARMM Regional Government | JICA | · POs were chosen by the community to implement the project, of good reputation and respected by the community and bounded by their accountability to deliver the project alone (and usually not affected by any political agenda).
· The MMSC should consider (as part of their review and approval) whether the community-based infrastructures identified in the subproject proposals are indeed what the communities need the most.
· Continued engagement, through program contract, with ARMM Social Welfare and Development Department in DSWD in the implementation of CDA is viewed as an effective mechanism to ensure maximum output. The partnership was premised on the capability of DSWD to deliver the services given more manpower complement at the field.
10. Widening Of GSO Road and Emergency Dredging Project, PHASE I (GSO I) | DPWH | KEDCF
11. Rural Road Network Development Project, PHASEII (RRNDP III) | DPWH | JICA | · Value Analysis in the project development cycle (i.e., conceptual stage, feasibility stage and/or implementation stage) is an important means to ensure project’s quality, performance and functionality while minimizing construction, operation and maintenance costs.
· For a proposed road rehabilitation project which identified certain road sections for exclusion, an efficient mechanism for the timely rehabilitation of these excluded road sections should be in place to maximize the benefits of the proposed project.
· For the DPWH to submit a project completion report (including the remaining subprojects once completed) which contains among others project outcomes and impacts, towards establishing that the objectives of the project were indeed achieved.
12. Rural Prower Project (RPP) | DBP |  | · Since it was already stipulated in the agreement and cannot easily be changed, it resulted to lower utilization of the PPF component.
· The design should have been complementation arrangement such as that in excess of the guarantee limit, the project should tap RPP-AF.
· Since not all clients are familiar with WB guidelines and processes, it is important to explain the significance of compliance with the Bank’s requirements.
· The Key Performance Indicator (KPI) should have been adjusted to include new customers connected through rehab and upgrading of distribution systems. The existing KPI only includes new customer provided with mini-grid electrical system or individual renewable energy technologies.
13. Northrail Project, PHASE I | NLRC | PROC | · Implementation was hampered by various types of delays such as relocation, financing concerns, review/evaluation/approval of design schemes, contractual disputes, etc. Based on project performance, it appears on hindsight that the proponent had underestimated these attendant risks.
· Better due diligence and greater clarity in the contractual provisions are needed prior to entering into a contractual arrangement in order to avoid conflicting interpretations.
· The importance of risk analysis during project appraisal and risk management especially during variations stage is underscored.
· In the course of project implementation, NLRC had various management teams at the helm. Management changes often require adjustments due to an initial learning curve.
· NLRC to complete valuation of the work done by the contractor to determine its counter claims relative to the arbitration proceedings.
· NLRC to complete the study of the new/redesigned project
14. Banaoang Pump Irrigation Project (BPIP) | NIA | ODA | · NIA reports that while the project facilitated the availability of dependable irrigation water supply resulting in improved crop production and subsequent better living conditions for farmer beneficiaries, some lessons learned include: (i) good management of funds and personnel development; and (ii) proper construction of structures and facilities.
15. Infrastructure for Rural Enhancement Sector (InfRES) Project | DA | ADB | · Project area coverage. Managing 92 sub-projects in nine regions proved to be organizationally challenging given the project’s lean structure, particularly in the areas of engineering, contract and financial management. Also, the level of inter-agency coordination and collaboration did not suffice, particularly during implementation.
· Quality should have prevailed over quantity of RI. More importantly, most participating LGUs had little or no experience in managing RI projects. Better assessment of LGU capacity should have been undertaken at the onset.
· Agricultural zoning. Future projects should be based on crop/land use zoning on a more macro-scale. Integrating or combining different types of rural infrastructure servicing large areas with agricultural expansion potential allow higher impact.
· This severely affected project coordination and provision of technical assistance to LGUs. In future projects, an actively functioning project management/steering committee should be mandatory throughout the project lifetime to provide overall project direction and policy guidance.
· For future projects, implementing agencies should assign full time permanent staff which can be trained to create a sustainable capacity that can function independently and effectively.
· Due to climate change, FMRs located in areas affected by much more frequent and higher rainfall must upgrade road engineering design including improved drainage, embankments and surfaces.
· LGUs should be encouraged to seek loans from other government financial institutions such as the Land Bank and the Development Bank of the Philippines. With simplified financial and accounting system, the IA and LGUs can concentrate more on the main elements of project implementation. Also, it is recommended that fund releases to LGUs be made based on actual work accomplishments rather than in tranches or advances.
16. Manila Third Sewerage Project (MTSP) | LBP | WB | · Most of the lands acquired used to put the treatment plants were provided by the LGUs for “free”. However, the free use of the land had corresponding “complimentary equities” attached to it such as covered sports/multi-purpose courts and improvements to the barangay office.
· The option to use conventional activated sludge process is a safe choice since it is proven technology and is robust in performance, i.e., can absorb shock loads. It is a conventional treatment process which provides stable treatment efficiently when operated properly.
· MTSP’s contribution to the overall improvement in the water quality was not expected to be significant even at appraisal given its relatively low financing proportion to MWCI. The higher value of the project was to be on the demonstration effect of alternative institutional and technical approaches to delivery of sewerage and sanitation services while complying with environmental standards.
· The increase in cost from the time of appraisal to implementation was mainly due to final designs reflecting a more accurate estimates and definite construction approaches. Project costs at appraisal were based on project concepts and feasibility studies.
[1] http://wwwagse.informatik.uni-kl.de/teaching/sppm/ss2012/presentation/03-SUCCESSReport06-Slides.pdf