## 5-A
Annex 5-A
CY 2013 ODA Portfolio Review
ODA Projects Supporting the Chapter and Sector Statements of the PDP
PDP-RM Chapter/Sector Outcome | PDP-RM Indicators Relevant to Project | IA | Project Title | Project Results as of December 2013 | Location/ Beneficiaries
Chapter 2: Macroeconomic Policy
Subsector Outcome: Sustainable fiscal sector achieved | (a) Higher government revenue-to-GDP ratio achieved (b) Tax revenue-to-GDP ratio improved | BIR | NPSTAR | eLAMS • Pilot implementation and nationwide roll-out in 6 May 2013 • Enhancements to eLAMS are as follows: (a) Captures additional system functionalities which are required to fully simulate the workflows involved in the audit cycle (b) Extends the functionality to TVN issuances and monitoring of LNs | Revenue District Offices, Assessment Service, concerned taxpayers
|  |  |  | eORB • Enhanced Electronic Letter of Authority Monitoring System • Pilot implementation done in La Suerte Cigar and Cigarette Factory on 27 November 2012 • Rolled-out to seven (7) tobacco taxpayers on > Enhanced Electronic Letter of Authority Monitoring System • Pilot implementation done in La Suerte Cigar and Cigarette Factory on November 27,2012 • Rolled-out to seven (7) tobacco taxpayers on 1 February 2013. | BIR National Office (Large Taxpayers Service), Revenue Regions, excise taxpayers
|  |  |  | Development of the Collection Reconciliation System • Rolled-out to BIR RR No. 7 Quezon City on May 2,2013 • Issuance of Operations Memo # 13-05-002 dated March 11, 2013 re: Pilot Implementation of CRS to selected offices in the BIR | BIR National Office (Collection Service), Revenue Regions, Revenue District Offices
|  | BIR | RARP | Automated Audit Tools • Completed conduct of training of 6 batches, with a total of 161 participants; • Issuance of the LTS Operations Memo No. 001-2013 dated April 18, 2013 (re: Computer Audit Program for LTS " Coalesced Audit for 2011) for the implementation of CAATTs in the 2011 audit have been approved alongside the CAATTs Manual as guide for the Revenue Officers | Large Taxpayers Service, large taxpayers
Revenue Collection per Audit • 2011 Baseline: 2.5M -No reported collections for 2011 cases have been submitted to date.
Chapter 3: Competitive and Innovative Industry and Services Sector
Globally competitive and Innovative industry and services sectors achieved | Employment generated from industry and services increased annually | DTI | RuMEPP | MSME employment generated: 74,633 (26% increase from 2012) | Cordillera Administrative Region (CAR), Bicol Region, Eastern Visayas Region, SOCCSKSARGEN Region, Caraga Region
Subsector Outcome 3b: Productivity and Innovative Capacity Increased | MSME Gross Value Added (GVA) increased (indicator based on original RM) | DTI | RuMEPP | Increased access of MEs to better financial services with about 77 MFIs now lending to 57,477 ME borrowers in RuMEPP program areas. | Cordillera Administrative Region (CAR), Bicol Region, Eastern Visayas Region, SOCCSKSARGEN Region, Caraga Region
Subsector Outcome 3d:Market Access Enhanced | Total approved investments increased | DTI | NICCEP | PhP4,295.62 million in investments generated | All regions
| Merchandise exports increased | DTI | NICCEP | US$ 2,847.74 million in exports generated | All regions
Chapter 4: Competitive and Sustainable Agriculture and Fisheries Sector
Sector Outcome: Competitive and sustainable agriculture and fisheries sector achieved
Sub-sector Outcome: Productivity in Agriculture and Fisheries sector increased | Rice self-sufficiency ratio increased | DA | RaFPEP | Distributed 803,750 bags of rice certified seeds (completed in September 2011) | CAR, Region II, III, IV-A, IV-B, V, VI, VII, VIII, IX, X, XII, XIII / Approximately 428,221 farmers
|  |  |  | There was a reported increase in rice yield by farmers in the FFS areas. - 11.95 % (Region VIII) reported a 11.95% - 7.32% (Region X) - 20.65% increase in the rice yield of the 1st batch and 2nd batch of FFSs conducted, respectively. | Region VIII and Region X / Approximately 4,279 farmers
| Annual proportion of farm households' income to total income decreased | LBP | SSLDIP | 28.54 km of farm-to-market road concreted | Dinalupihan, Zamboanga Sibugay; Sipalay City and San Mateo, Isabela / 7,901 households
Chapter 5: Resilient and Inclusive Financial System
Chapter 6: Social Development
Sector- Human capabilities improved Sub-Sector Outcome: Health and nutrition status improved | Maternal mortality rate per 100,000 livebirths decreased Infant mortality rate per 1,000 livebirths decreased | DOH | 2WHSMP | 80% of births delivered in a health facility (target for 2013:80%) | Sorsogon / 93% Surigao del Sur / 88% Albay / 96% Catanduanes / 88% Masbate / 71%
| Maternal mortality rate per 100,00 livebirths decreased CPR all methods increased |  |  | Increase in CPR by 10 percentage points | Sorsogon / Increased by 1% Surigao del Sur / Decreased by 2% Albay / Increased by 1% Catanduanes / Increased by 5% Masbate / Increased by 8%
Subsector Outcome- health and nutrition status improved | • maternal mortality rate per 100,000 livebirths decreased • National health insurance program enrolment rate increased |  |  | 55 % of deliveries in BEmONCs in each project LGus is financed by PhilHealth sponsored programs target for 2013: 40%) | Sorsogon / 20% Surigao del Sur / 46% Albay / 35% Catanduanes / 70% Masbate / 20%
| • maternal mortality rate per 100,000 livebirths decreased • National health insurance program enrolment rate increased | DOH | HSRA-SP | Utilization rate of the participating hospitals higher than 80% but lower than 105%
100 percent of participating hospitals are PhilHealth accredited
75% of patients at secondary hospitals has been referred from primary care providers or private practitioners
| Maternal mortality rate per 100,000 livebirths decreased Infant mortality rate per 1,000 livebirths decrease CPR increased | DOH | USAID Health Agreement (Family Health Improved) 1. Family Planning | 37% CPR for modern methods Target :38% ACTUAL: awaiting result survey First birth at 18 Target:10% Actual:awaiting results survey -Couple of years protection(CYP) in USG-supported programs Target: 1,400,000 Actual:1,500,000 -Percent of USG-assisted service delivery sites providing FP counselling and/or services Target:34% Actual:64%
|  |  | Maternal and child health | Percent of births attended by skilled doctor,nurse or midwife Target: 80% Actual: awaiting results survey
| Tb case detection decreased |  | 3. Tuberculosis | Percent of registered new smear positive pulmonary TB cases that were cured and completed treatment under DOTS (Treatment success rate) Target: 92% Actual: 90% Case notification rate in new putum smear positive pulmonary TB cases per 100,000 population nationally Target: 88% Actual: 90% | Nationwide
| • maternal mortality rate per 100,00 livebirths decreased • National health insurance program enrolment rate increased | DOH | EU-Health Sector Policy Support Programme II 1.Health Financing | Increased financial protection especially of poor woman and men through extended social health insurance coverage -enrollment of the NHTS poor is increasing over the years ( from 5.2 M in 2011 to 8.03 in 2012)
|  |  | 2. Health Regulation | Improved Accessibility, quality and safety of health products and services -construction/repair of health facilities and procurement of medical/hospital/laboratory equipment still ongoing
|  |  | Service Delivery | Increased utilization of quality primary health services, including safe water and sanitation especially by the poor and vulnerable and disadvantageous population groups (IP,GIDAs) -continuous increase of women giving birth in health facilities and attended by skilled birth attendants
Sub-Sector Outcome: (1) Access to quality health and nutrition services improved Access to quality education, training, and culture improved |  | DSWD | KC-AF, KC-MCC | • 399 health stations • 423 day care centers • 742 school buildings | 397 barangays, 100,941 HHs 416 barangays, 75,291 HHs 745 barangays, 181,494 HHs
Sub-Sector Outcome: Knowledge and Skills Enhanced | *Net enrolment rate increased *Achievement rate increased | DepEd | Support to Philippines Basic Education Reforms (SPHERE) | BESR-SPHERE contributed to improvements in learning outcomes as observed in increases in achievement rate from 65% in 2007 to 67% in 2012. It also contributed to improvements in participation rate from 88% in 2007 to 91% in 2012.
| *Net enrolment rate increased | DepEd | Basic Education Assistance for Muslim Mindanao (BEAM)-ARMM | Observable improvements in health seeking behaviors of school children and in health conditions of schools which led to reduced absenteeism and improved performance of pupils. | ARMM
Chapter 7: Good Governance and the Rule of Law
Sector Outcome: Effective and transparent governance practiced | Not yet identified | BIR | NPSTAR | Procurement of Software Solution for Tax Rulings and Case Management System • Pilot Roll-out of Tax Rulings and Case Management System (TRCMS) at the offices under LIG started on May 28, 2013 per Memoramdum dated May 27, 2013 Quezon City on May 2,201 • Issuance of Operations Memo # 13-05-002 dated March 11, 2013 re: Pilot Implementation of CRS to selected offices in the BIR | BIR National Office (Legal Service), Regional Offices, taxpayers
|  |  |  | eAccReg & eSales • Pilot roll-out on June 27, 2013 at LTS and RDO # 30, Binondo Issued Operations Memo dated July 18, 2013 re: Guidelines for the Pilot Implementation eAccReg (eSales) | BIR National Office, Regional Offices, Revenue District Offices, taxpayers
|  | BIR | RARP | Procurement of Software Solution for Tax Rulings and Case Management System • On-going development for Work package 1.1 covering registration for LTS; • User Acceptance Testing for Work package 1.1 started on Dec. 5, 2013; • Requirements validation and data mapping for Work package 1.2 in progress; • Change Management Plan finalized; • There are delays in UAT schedule of Work Package 1.1 due to Hardware issues and slow response time which in effect has hindered the progress of Work Package 1.2 and 2.0 as well • Schedule for Work Package 2.0 will slide to 2015 | Large Taxpayers Service, large taxpayers
Public Awareness Campaign • Contract signing with consultant on 27 September 2013 • Proposed tax information ads were presented for comments; • "Register, File, Pay" Storyboard being developed.
Chapter 8: Peace and Security
Chapter 9: Sustainable and Climate-Resilient Environment and Natural Resources
Sector Outcome: Sustainable and climate resilient environment and natural resources achieved
Sub sector outcome 2: Sustainably managed natural resources achieved | Biodiversity protection and conservation improved | DENR | ICRMP | 79 LGUs (out of 80) have adopted their plans; 70 (89%) of them have regularly allocated budget (from their 20% development and general/ regular fund) for implementation of the plan | LGUs in 7 provinces (Cagayan, Zambales, Romblon, Cebu, Siquijor and Davao Oriental) / General Population
(sub-sector outcome) Environmental quality improved for a healthier and cleaner environment | BOD level of Laguna Lake within standard at 7 mg/L | LLDA | LISCOP | 79,987 MT/yr (with projected reduction by 307 MT/yr, with the implementation of MRF projects under LISCOP) | Laguna Lake
Chapter 10: Accelerating Infrastructure Development
Sector Outcome 10b: Environmental quality for a cleaner and healthier environment improved | Industrial Pollution Control Volume of wastewater treated (m3/day) Amount of pollutant removed (kg/day BOD) | DBP | EDP | 420 7.56 | Laguna, Talisay, Dasmariñas (Cavite), Mangantarem (Pangasinan), Ildofonso (Bulacan), Olongapo City, Digos City,Butuan City, Sibonga (Cebu), Zamboanga City, Balamban (Cebu), Toledo City (Cebu), Biñan (Laguna), Parañaque, Cebu City, Minglanilla (Cebu), Tarlac City / 17
| Solid Health Care/Hazardous Waste Management Solid waste treated (kg/day) Waste Collected (kg/day) |  |  | 128,000 7,027,000 | Placer (Masbate), Calbayog (Samar), Gen. Santos City, San Pedro (Laguna), Butuan City, Malay (Aklan), Iligan City, Digos City, San Jose (Romblon), Naga (Cebu), Olongapo City, Iloilo City, Calbayog City, Surigao City, Consolacio City (Cebu), Lake Sebu (South Cotabato, Iriga City (Camarines Sur), M’lang (North Cotabato), Gattaan (Cagayan), Bislig (Surigao del Sur) / 20
| New and Renewable Energy Additional Connections |  |  | 5,579 | Sultan Kudarat, Leyte, Davao del Sur, Bohol, Oriental Mindoro, Romblon, Loreto, Camarines Sur, Cotabato / 10
| Water Supply Additional household connections Additional Volume of Water Supply (m3/day) Increase in Revenue in Water |  |  | 37,795 additional connections 1,417,526.63 m3/day additional volume of water supply PhP105,045.33 | Boracay Island, Tarlac City, Bocau (Bulacan), Hinunangan (Southern Leyte), Ilagan (Isabela), CamarinesNorte, Angeles City, Laguna, Cebu, Valencia (Bukidnon), Padre Garcia (Batangas), Moises Padilla (Negros Occ.), Digos City, Aurora (Zamboanga del Sur), Puerto Princesa / 15
Sanitation Volume of wastewater treated (m3/day)
Accelerating Infrastructure Development Intermediate Outcome 10a: Competitiveness enhanced and productivity increased in the industry, services and agriculture sectors | Increased displaced carbon dioxide (CO2), in metric tons Electricity and fuel conserved, in Kilo Tons Oil Equivalent (KTOE) | DOE | PEEP | Estimated annual equivalent CO2 emission reduction of 167,500 tons/year is being realized due to the distribution of 8.6 million CFLs, retrofitting of 35 government buildings, park lights, street lights and traffic lights The project contributed 78.22 KTOE per annum. | Nationwide
| Increased sitios with electricity RE capacity increased (% of total capacity installed) |  | AMORE | Energized 5,507 households with either solar home lighting or solar lantern | Mindanao
Intermediate Outcome: Quality, adequacy, and accessibility of infrastructure facilities and services enhanced |  | DSWD | KC-AF, KC-MCC | • 460 water systems • 406 roads and bridges • 49 sanitation facilities 42 electrification facilities | 475barangays, 104,393 HHs 431barangays, 103,317 HHs 49 barangays, 3,109 HHs 42 barangays, 6,698 HHs
| • Proportion of households with access to water supply increased by 3.41 percentage points from 84.80% in 2010 to 88.21% in 2016 (out a total of 20.2 million households as of 2010). Flood Control | LBP | SSLDIP | 22 Level III water supply completed and operational. 5.59 km of drainage have been laid | Nationwide / 42,320 households have access to potable water 24/7 Candon, Ilocos Sur / 1,224 households