## 7A
Annex 7-A
CY 2013 ODA Portfolio Review
Actions Taken on Recommendations from CY 2012 Review
Recommendation | Action Taken / Status
Economic Sector
DA
For MRDP 2: After completion of the damage assessment by the RPCO, prepare a concrete Action Plan on measures to be taken concerning project outputs damaged by typhoon Pablo. | -
For CHARMP 2: Fast track implementation of the RID component given the one year extension granted by the ICC | -
For CHARMP 2: Closely monitor the project’s Action Plan and projected loan disbursement schedule | -
For RaFPEP: As recommended by the IFAD SIS Mission in September-October 2012, populate and complete the database for RaFPEP | -
For INFRES: Closely monitor the implementation and completion of the remaining works which are expected to be completed by April 2013 | -
DAR
For ARCP 2: For DAR to swiftly finalize which of the following options shall be pursued: (a) synchronize closing date of OFID loan (31 December 2013) with ADB loan (30 June 2015); (b) application of 90-10 NG-LGU cost sharing scheme for subprojects pipelined for 2013-2014; and (c) request for change in project scope if disbursement levels will not improve. | DAR requested 1 year loan validity extension (until 31 December 2014) under OFID. ICC-CC approved the said request and endorsed to DOF, which the later also endorsed to OFID for concurrence. OFID, on its 20 August 2013 letter to DOF, concurred the said request. For NG-LGU Cost sharing, DAR Management resorted to other option to help LGUs, putting the value on some in-kind contributions by the LGUs to lessen their cash contribution, among others.
For TPKP: Fast track the completion of bridge construction within the target period. | To continue the construction of the remaining bridges, a MOA among DAR, DPWH and the supplier (Matiere S.A.S.) has been finalized for immediate signing of the principals. The said MOA stipulates, among others, the release of the remaining loan proceed from BNP Paribas (creditor) to Matiere S.A.S. (supplier) prior to loan closing.
For IARCDSP and MinSAAD: Based on DAR’s experience in implementing ARCP2, the Department must take aggressive measures in resolving LGU-related issues particularly with the implications of the results of 2013 elections. | Reconfirmed with the newly-elected officials their commitments to with the project and provide required equity.
DENR
For ICRMP: Facilitate resolution of issues concerning implementation of components A (IEC and PHE); and D (Social and Environmental Services and Facilities) to ensure completion of planned activities by proposed revised closing date of June 2014. | The consultants have already completed the remaining three (3) policy studies. Final reports are for presentation to the ICRMP TWG for acceptance. The Policy IEC Materials on National ICM Program, Foreshore Management, Mangrove Management, and User Fees and Resource Rents have been finalized and are ready for printing and distribution. On PHE IEC Campaign, a training-workshop on “Integrated Approaches to Population Health and Environment” was conducted last Feb. 29-Mar 2, 2013, in collaboration with PATH Foundation. Five (5) site specific IEC activities per region were identified during the training. Adoption of the Direct Payment procedure to finance construction of LGU subprojects to address depletion of the MDFO imprest account resulted to the resumption of construction activities and completion of 5 out of 15 LGU subprojects. Close monitoring of field level activities are continuously being done.
Adoption of the Direct Payment procedure to finance construction of LGU subprojects to address depletion of the MDFO imprest account resulted to the resumption of construction activities and completion of 5 out of 15 LGU subprojects. Close monitoring of field level activities are continuously being done.
For NPSENRMP: FASPO and other oversight offices to closely monitor the progress of preparation of liquidation reports of the concerned units and provide constant reminders, if necessary. | Financial Management Service (FMS) and FASPO conducted series of financial validation and reconciliation to concerned regions to facilitate submission of liquidation reports of NPS-ENRMP related expenditures. It was likewise supplemented with a Memorandum issued by FMS to concerned Bureaus/Regions/Offices reminding them of the submission of said liquidation reports. FMS is currently consolidating the reports, for subsequent endorsement to WB, deadline is until end of April 2014.
For NPSENRMP: National Greening Program (NGP)-National Coordinating Office, FMB and FASPO to continue to provide assistance to the Regions and coordinate with CSOs involved in the NGP in identifying bottlenecks that are causing delays in seedling production | FMB and NGP is continuously monitoring NGP activities and providing TA and guidance to field offices. Reporting of Status of NGP implementation being done during the weekly DENR ExeCom Meeting
For CBFMMP: Training for DENR and LGU staff to focus on: • Financial procedures for liquidation and replenishment of funds • Coaching and mentoring of POs and communities on CBFM Modules under the ENRD Program | Conducted re-orientation on Financial Management System on selected slow-moving LGUs. The PMU continues to undertake coaching and mentoring to the LGUs on financial procedures to facilitate liquidation and replenishments of funds.
For CBFMMP: Identify exit strategy measures to enhance sustainability, including the finalization of guidelines on co-management and conclusion of co-management agreements with LGUs. | Beginning CY 2013, the Project started the conduct of CBFMA orientation to potential POs, for subsequent issuance of said tenurial instrument. The existing Certificate of Stewardship Contract (CSCs) which have already expired and being evaluated for purposes of renewal. The issuance and renewal of appropriate tenurial instrument would help address sustainability of project measures introduced in the area.
For CBFMMP: Finalize the socio-economic baseline study and update the existing cost benefit studies of NRM and infrastructure Projects; | A specific baseline study has been completed for infra/livelihood project in Negros Oriental: • Small water impounding projects (SWIPs) and aquaculture in Bayawan City • Sawmill and SWIP in the Municipality of Bindoy
For CBFMMP: Improve dissemination of communication of results and guidelines at all levels | The Operations Guidelines for the LGUs have been distributed and updating is now on-going. IEC activities are continuously being undertaken following the Communication Plan developed by the Project.
For CBFMMP: DENR and LGUs should ensure that LGUs are able to operate and maintain equipment/machineries provided by the project. | It is already considered in the M and E activities of the individual Site Coordinators of the CBFMMP, together with the counterpart from Land Bank of the Philippines.
For CBFMMP: Possible extension of consulting services beyond 2013. | The request for Addendum of the DFS Contract to extend the services of the National and other short-term consultants was already endorsed to the KfW, for issuance of “no objection letter”.
NIA
For ARIIP: Decide whether to pursue the requests for change in scope, cost increase and loan validity extension | Project was remanded back to ICC-TB in July 2013, where ICC-TB recommended that NIA repackage the proposed ARIIP restructuring into an entirely new project.
For HCAAP: Draw up an Action Plan on the completion of the remaining works which shall be funded by GOP funds. | -
For PIDP: Fast-track implementation especially on the Civil Works component. | NTPs were issued for 14 civil works contracts in 2013.
For PIDP: Resolve the issue on the Rat Plan funding gap considering that the Rat Plan should be completed by December 2012. | -
For PIDP: Determine next steps after the NIA Rat Plan. | -
For NISRIP: Comply with DBM requirements for requested plantilla positions and expedite filling up of key PMO personnel. | -
Infrastructure Sector
DBP
For EDP: Continue the marketing efforts being done to discuss issues and concerns of the prospective borrowers. | With assistance of the EDP-TA, the PMO undertook briefings to potential clients (LGUs, private sector, industry associations) and partner agencies (DENR-EMB, NSWMC, DOE etc.). Based on approved and pipeline projects, expected disbursements are estimated at Yen, 790 million for 4th Quarter 2013; Yen 6.965 billion for FY 2014; and Yen 6.946 billion for FY 2015 Substitute accounts are being sought in case accounts that are in the pipeline are delisted or on hold due to withdrawal of borrower or if there is insufficient documentation among others DBP-PMO is closely coordinating with Account Officers of its branches to facilitate reviews/approvals. For New & Renewable Energy (NRE) and Water Supply projects, a total of nine (9) substitute accounts were added as of December 31, 2013 amounting to PhP 2.102 billion DBP is also pursuing the water districts with completed septage feasibility studies funded thru the USAID PWRF Support Program this 1st Quarter of 2014 Continued coordination among Marketing Units, Fund Sourcing and PMO. In a parallel effort, DBP-PMO is also pursuing private sector proponent (PSP) for EDP. Total loan approval for PWRF amounted to PhP 3.432 billion of which 86% or PhP 2.892 billion came from the private sector participation. This already exceeds the PWRF allocation of JPY 5 billion. Additional reallocation under PWRF will depend on project disbursements.
For RIGP: Continue the marketing efforts being done to discuss issues and concerns of the prospective borrowers. | Build pipeline projects especially for disaster-stricken areas in coordination with the DBP Branches/Marketing Units.
For EDP: Closely monitor the approvals of the proposed sub-loans. | Updates on releases to approved sub-loans/end-beneficiaries are being reported during the Monthly Monitoring Meetings between JICA and DBP.
For EDP: Coordinate with DOF-CAG and BSP to reduce processing time of borrowers compliance to the Monetary Board Opinion Requirement. | Requisite MB Opinion for two approved EDP sub-projects was already secured.
For EDP: Explore options to fast track loan releases of approved subprojects. | Discussed through the monthly DBP-JICA monthly monitoring meetings. In said meetings not only releases to end-beneficiaries were discussed but also the 4-month disbursement commitments of the Bank and other issues such as concurrences to be secured for big ticket accounts and possible support to calamity-affected borrowers (if any). As an initiative to improve disbursement performance and catch up with the committed target, a request for a reallocation of sub-category funds (from Category B (EDP-Non Water) to Category A (EDP-PWRF)) and an increase in initial deposit on the Special Account of the EDP-PWRF was submitted to NEDA on March 14, 2014.
For RP-AF: Submit Project Completion Report of the RP-AF | An ICR prepared by WB was received by NEDA in 2013.
For CBCHP: Explore mixing of ADB funds with DBP funds to reduce interest rates to sub-borrowers. | Explored mixing of ADB funds with DBP funds to reduce interest rates to sub-borrowers.
For CBCHP: Full blast marketing efforts in coordination with the marketing units. | Full blast marketing efforts in coordination with the marketing units.
DILG
For the PMOs to track all the ODA loan and grant projects implemented by DILG and submit regular quarterly and semestral reports on their accomplishments and outputs for loans and grants respectively. | Some of the projects provided regular reports (e.g. BFP Capability Building Program for Selected Priority Cities, Philippines Poverty-Environment Initiative Phase II).
For DILG Central Office to strengthen its M&E of FAPs including the improvement of database and availability of information. | In the implementation of the recently approved DILG Rationalization Plan, the Monitoring and Evaluation Division under the Planning Service was established.
DOE
Closely monitor the financial and physical aspects of the project. | Implementers were required to submit physical and financial accomplishments of their respective projects; and, summaries of fund utilization of projects were requested from the Budget Division of the DOE. DOE requested for reallocation of loan proceeds for PEEP loan due to the change in scope earlier approved by the ICC in October 2011. A partial cancellation of US$1.825 (loan savings) was also requested.
Continue submission of quarterly progress reports of ongoing projects in order to facilitate issue/resolution during implementation | Quarterly reports for some foreign-assisted projects (ODA) and locally-funded projects were submitted to NEDA-MES. Other progress reports of grants funded projects still need to be regularly submitted.
Preparation/Submission of Project Completion Report for the PEEP. | DOE was requested to submit PEEP Project Completion Report.
Enhance M&E system to fully document outputs, outcomes as well as lessons learned of projects. | DOE signed a Memorandum of Agreement with the Department of Science and Technology-Advanced Science and Technology Institute (DOST-ASTI) for the design, development and customization of ASTI Infosys for the DOE, which include a module on Program and Project Management Information System.
DOST
For the Improvement of the Flood Forecasting and Warning System for Magat Dam and Downstream: To finalize project’s technical specifications and bidding documents to commence implementation. | As of March 2014, the project’s technical specifications were finalized. PAGASA already sent their draft Terms of Reference and their proposed type of bidding procedure to the donor. Currently, PAGASA is waiting for NoRAD’s comments for finalization.
To submit regular reports of their ongoing projects’ accomplishments and outputs. | Only one project provides regular updates (i.e. Grant Aid for the Project for Improvement of Equipment for Disaster Risk Management)
DOTC
On CNS/ATM: with the new loan extension approved by the ICC, the DOTC-CAAP is enjoined to exert the necessary efforts to ensure the immediate implementation to facilitate completion of the project, taking into consideration project milestones it has committed to achieve, in order to finally realize the long delayed project benefits accruing to an upgraded CNS/ATM Systems. | Works resumed in August 2013.
On GMA Ports Project: DOTC/PCG to submit soonest the required documents to allow ICC approval process of the proposed substitute project (Philippine Port and Coast Guard Capability Development Project). If ICC approves the substitute project, the DOTC to fast-track finalization of the amended contract and immediately start implementation. | Proposed project was approved by the NEDA Board on 21 November 2013 and endorsed by DOF to BNP Paribas in January 2014. Currently, approval of the Bank is being awaited.
On Laguindingan Airport: DOTC-CAAP to reconsider its plan to open the airport prior to complete installation of the ANS support facilities to address concerns on air transport passenger safety | Airport made operational under Visual Flight Rule
DPWH
For RIIDP: with the expected completion of the procurement for Consultant and Contractors, to immediately report back to ICC the final configuration (i.e., changes in the 2011 ICC-approved scope and cost) of the project | Still to be complied. Different options on how to proceed with implementation showing cost implications were presented to the DPWH Secretary for decision. Selected option will be submitted to ICC for approval in 2014.
For BC/RP: to ensure that the necessary local funds required for the turn-key construction of the 43 bridges, which were supposedly to be funded by the Supplemental loan, are included in the DPWH budget. | Complied. Modification of the 2013 budget from loan proceeds to GPH was approved, whereby six bridges had been funded. Pre-construction of three bridges have been completed while the NTP of the three other bridges is to be issued in January 2014.But later in 2013, the DPWH in consultation with DOF, NEDA and DFA decided to resume works using the ICC-approved supplemental loan. The MOU between GPH and GOS is still under preparation.
For POPSTIRP: with the recent approval of ICC on its request to include the additional 15 subprojects, to provide NEDA a copy of the RDC endorsement for the additional roads and bridges subproject once secured. | Complied. RDC endorsement for the subprojects submitted on 22 July 2013
For CLLEX and RUPP: to fast-track the procurement process as it has already delayed the projects. DPWH to decide on the Failure of Bidding issue and to respond to JICA’s request, specifically for CLLEX. | Complied. Close coordination/monitoring with BAC-TWG and strict adherence to Project Procurement Management Plan to fast track the procurement. On CLLEX failed bidding, the BAC for Consultancy Services after a series of deliberations agreed to award the contract. The BAC Resolution was approved by the DPWH Secretary last 2 July 2013, contract was signed on 30 August 2013 and the NTP was issued on 12 September 2013.
For BSAAR: once loan extension is approved by the ICC and KEDCF, to ensure better implementation to avoid further major issues/bottlenecks that needs ICC approval. | Physical implementation completed within the revised loan closing date. But another loan extension is necessary to effect processing and payment of contractual obligations.
For MCC-PMO: to immediately report to ICC the divergence in the project details which reflects the change in project scope from the original ICC approval | -
For MBURD: with the closure of the loan in September 2013, to expedite loan disbursements to maximize utilization, and to secure the necessary budget cover to fund the 20 percent works on flyover construction foreseen to spill over until 2014. | MOA between DPWH and the supplier was signed on 25 June 2013. The MOA effects the appropriate procedure for the completion of the contract after loan closing, to include the opening of/drawing from an escrow account.
For MRIP, BC/RP, MBURDP & POPSTIRP: to continue reporting on project components being/expected to be implemented using local funds. | Continuing
For RRNDP III: to study the recommendation made by the RPMC-CARAGA on the flooding along Esperanza-Bayugan road and provide the necessary action to be taken on the issue raised. | PMO is requesting authority to procure works for the raising of grade at Sta. 48+000 to Sta. 48+8000 at about 880 lineal meters.
For PMRCIP-II: to complete all physical deliverables under PMRCIP-II within the original time scope of August 2013 since DPWH request for additional scope and cost increase was approved by the ICC-Technical Board on 21 November 2012. Furthermore, since overall physical accomplishment (including the new scope) is at 98% as of December 2012, DPWH should implement an effective exit strategy to ensure that proper O&M institutional arrangements are in place. | -
For PHUMP-III: to complete the procurement process of Contract Packages 1 and 7 that covers road raising and the construction of local drainage channels and bridges. Furthermore, DPWH should facilitate the signing of a MOA with the concerned LGUs for the future O&M of project structures. | -
With the upcoming local election in May 2013, DPWH to closely coordinate with the concerned LGUs with regard the O&M portion of completed projects. | -
LBP
For CLEECP: LBP to immediately decide on the possible restructuring of the project (i.e. further extension of the loan closing date and possible change in scope) as the CLEECP loan is already closing in June 2013. | Due to non-utilization of the CLEECP funds, LBP and KfW agreed to conduct an evaluation / study of the project and re-design same in order to overcome obstacles in the project implementation. The Consultant which was commissioned by KfW to conduct the study submitted the results of its study in December 2013. LBP met with KfW-CLEECP Project Manager, Ms. Tanja Tonison on 27 February 2014 to discuss LBP comments on the study and the next steps concerning CLEECP.The Program Manager is currently confirming whether there are firm pipeline projects which will serve as basis for its decision before June 2014 and decide whether or not it will continue with the project implementation based on the new project design. There are on-going exchanges of communication between LBP and KfW.
For SSLDIP: Consider a more realistic targeting in terms of schedule/duration of project implementation. Since the loan validity is already on its extension period, there is a need to revisit timelines of subprojects implementation to avoid further extension of the loan validity. Coordinate with DOF-CAG and BSP to reduce processing time of borrowers’ compliance to the Monetary Board Opinion Requirement. | In view of the rehabilitation requirements of LGUs affected by the recent calamities, LBP requested WB’s approval of the reprogramming/restructuring of SSLDIP as follows: • The SSLDIP uncommitted funds amounting to P 419.14 million shall be utilized for rehabilitation efforts in areas affected by Typhoon Yolanda. • There will be revisions in the terms and conditions of SSLDIP based on discussions with the World Bank DOF submitted its endorsement to WB on the said request on 3 February 2014. GPH is yet to receive reply from World Bank.
For MTSP and LIP II: Submit Project Completion Report. Lessons learned, outputs and outcomes of completed projects/subprojects should be fully documented. | LBP has already complied with the submission of PCR for MTSP. For LIP II, the PCR is still being prepared by the Program Manager. However, PCRs should include outcomes from completed subprojects.
Continue the conduct of orientation and briefing to all project stakeholders on the project objectives and requirements of the Development Partners to ensure continued support of the projects. | LBP conducts road shows and LGU summits nationwide in order to inform its clients/project stakeholders on the various facilities of the Bank.
Social Sector
BIR
For NPSTAR: Stricter quality control measures, i.e., more rigid NPSTAR monitoring/evaluation as it is already nearing loan closing to ensure most of the target outputs are completed and use of loan proceeds maximized. | NPSTAR component outputs were delivered within Project completion date.
For NPSTAR: Tighter sanctions/penalties for contractors for delays in deliverables.
DepEd
Ensure availability of baseline figures, realistic target-setting and implementation monitoring | -
Conduct inventory of existing ODA –assisted projects to determine gaps, redundancies and overlaps of completed and ongoing projects | Development of DepEd’s Project Management Information System (PMIS), commenced last April 2012. PMIS is a database for tracking progress of programs and projects. (Request for updates)
Converge/ coordinate with other offices inside DepEd of a unified M&E system to cover all existing projects and programs regardless of funding sources | -
Strengthen coordination with various development partners to regularly provide monitoring reports | -
Strictly comply with regular submission of status reports to NEDA-PMS (quarterly for loans; semestral for grants) | Continuous tracking of all projects
Trim down project indicators for ease of monitoring i.e., focus on key indicators of project final outputs/ deliverables | -
SC
For JRSP: Compliance with WB recommendations in its June to July 2012 mission. | Ongoing conduct of impact evaluation of the APJR
For JRSP: Adoption of an effective exit strategy | -