## 7B
Annex 7-B
CY 2013 ODA Portfolio Review
Recommendations for CY 2014 and Beyond for Implementing Agencies
Project / Issues | Recommendation / Action Plan | Timelines | Responsibility Center
Bureau of Internal Revenue (BIR)
NPSTAR | Document lessons learned on the implementation of NPSTAR |  | BIR - PMIS
NPSTAR | Consider conduct of ex-post evaluation of NPSTAR |  | BIR - PMIS
| Prepare Program Completion Report (PCR) |  | BIR – PMIS & WB
RARP / Monitoring and evaluation; Reporting on progress | Report on the implementation issues of the RARP |  | BIR/ DOF & RIPS
RARP / Project Implementation | Fast-track RARP implementation considering a wide gap of elapsed time vis-à-vis financial disbursements |  | BIR/ DOF & RIPS
Department of Agriculture (DA)
RaFPEP | Follow-up countersigning of the FA for the Supplementary Financing with the DOF | Immediately (before 30 June 2014) | DA
CHARMP2 | With the OFID loan set to close in July 2014, the necessary ICC documents should be submitted to NEDA for review and processing. (Update: The NEDA ICC-TB during the 18 March 2014 approved the one-year request for loan extension from July 2014 to July 2015.) | Before July 2014 | CHARMP2-PMO
MRDP2 | Implement a sustainability plan and exit strategy in the remaining months of the project until loan closing in December 2013 | April-December 2014 | MRDP2-PMO
CHARMP2 | Closely monitor catch-up plan to ensure completion by end of December 2014 | April-December 2014 | CHARMP2-PMO
MRDP2 | Start preparatory activities for the Project Completion Report. | Before December 2014 | MRDP2-PMO
RaFPEP | Implement rehabilitation plan for completed outputs but were partially/severely damaged during the year | 2014-2015 | RafPEP-PMO
All loans and grants | Take stock and report on results (outcomes and impacts). | Continuous | DA
Department of Agrarian Reform (DAR)
ARISP3 | DAR to request DBM issuance of additional appropriation to cover the foreign exchange differentials for consulting services and the release of the reverted amount worth PhP 195.6 million for civil works | ASAP | DAR, DBM
ARCP2 | Continue to fast track implementation particularly under OFID loan | Until loan closing (December 2014) | DAR
ARCP2 | Re-assess project accomplishment particularly under ADB loan which DAR indicated the possibility to request one year extension | June 2014 | DAR
TPKP | Firm up its plan of action to complete the installation of the remaining bridging materials or construction of remaining bridges and provide copy to NEDA for continues monitoring under closed loan with incomplete output | ASAP | DAR
TPKP | Immediate signing of MOA among DAR, Matiere S.A.S, and DPWH | ASAP | DAR, Matiere S.A.S, and DPWH
MinSAAD | Weigh other options (e.g. re-bid the hiring of consulting firm or bid per package) which could minimize further implementation delays while waiting for Follow-through GPPB decision with regard to bid failure for consulting firm which DAR and JICA have differing views and the decision of the later not to give concurrence on the Bid failure report for consulting firm | ASAP | DAR, JICA, and GPPB
IARCDSP | DAR to assign new project manager immediately to prevent delays | April 2014 | DAR
Development Bank of the Philippines (DBP)
RIGP | Follow-up the Sub-loan Agreement with WB | Immediate
| Submit the details of activities relative to its proposal on Yolanda; | Second quarter 2014
Finalize proposal should DBP decide to push through with the two-year loan extension
EDP | Review the financial status and submit proposal to increase special account under the Water Loan Category, if necessary | First quarter 2014
LDIP | Given the recent approval of ICC on the expansion of eligible subprojects, DBP to comply with conditions set by the ICC: (i) submit a policy brief ensuring ICC that LIDP will not displace private lending; and (ii) report to ICC and improved performance arising from the expanded list of eligible subprojects within the provisional 1.5 years | Starting second quarter 2014
CBHCP | Adhere to the ICC decision to market/lend PhP586 million with priority clients as follows: (i) PhP300 million for LGUs; and (ii) PhP286 million for “pro-poor” private health facilities and Public Private Partnership projects DBP and NEDA-MES to conduct semestral reviews to assess project implementation | Continuing March and August 2014
All Projects | Continue proactive marketing the facilities to the potential clients/borrowers Monitor/Document initial results/outcomes of completed subprojects Negotiate with DOF on the reduction of FOREX and guarantee fee charges DBP to report on results and outcomes of their projects | Continuing January 2014
Department of Environment and Natural Resources (DENR)
CBFMMP | The action planning with the LGUs in Panay formulate the catch up plan per LGUs to facilitate achievement of target accomplishments | First quarter 2014 | DENR
CBFMMP | Meeting with slow moving LGUs will be undertaken within to decide on possible transfer of funds to fast moving LGUs | First quarter 2014 | DENR
CBFMMP | An additional M&E Team will be organized to cover all M&E requests from the LGUs to facilitate payment of completed activities | 2014 | DENR
ICRMP | Facilitate liquidation of funds in time for project completion in June 2014. Continued provision of technical assistance to field finance officers as well as LGUs in the preparation of SOEs | 2014 | DENR
ICRMP | Coordination meetings with LGUs to fast rack approval of the incentive/disincentive mechanisms to be adopted by LGUs before project completion in 2014 | First quarter 2014 | DENR
ICRMP | Prepare Project Completion Report for the project | Second quarter 2014 | DENR
NPSENRMP | Prepare Project Completion Report | 2014 | DENR
NPSENRMP | Complete liquidation of funds | 2014 | DENR
FMP | Fastrack procurement of consulting services | First quarter 2014 | DENR
PhilCCAP | Follow up request submitted to the WB, thru DoF, for proposed increase in the threshold amounts in their respective designated accounts | First semester 2014 | DA and DENR
EnRD | Lobby for NDRRMC and OCD to come up with the guidelines on the preparation of DRRMPs | 2014 | DA, DENR
| Solicit support from NDRRMC, OCD and Pag-asa to include LFEWS as strategy for disaster preparedness | 2014 | DENR, DA
Department of Education (DepEd)
Monitoring and Evaluation | Prepare Program Completion Report (PCR)/Document lessons learned of SPHERE which closed in 2013/ on the implementation of SPHERE and other projects which closed in 2013 |  | DepEd - PDED& DepEd - EDPITAF
Monitoring and Evaluation | Consider conduct of ex-post evaluation of projects which closed in 2013 or in previous years |  | DepEd - PDED
Activity reporting (USAID – Assisted Project) | Strengthen reporting mechanisms of USAID contractors to the OPS – PDED to promote DepEd ownership of the Projects |  | USAID/ DepEd - EDPITAF
Program Implementation (BEAM – ARMM) | Support priority action points as identified in the ‘as of December 2013’ progress report which includes the following, among others: • conduct of DepEd ARMM needs assessment • establish baselines across three (3) proposed evaluation studies • promote formalised and scheduled quarterly meetings among the implementing partners M&E staff |  | DepEd – ARMM
SBP4BE, EPIP & PRIME | Fast track implementation of Projects considering closing period at the later part of the year |  | DepEd – EDPITAF
Department of Interior and Local Government (DILG)
All projects | Active tracking, monitoring and evaluation of all the ODA-funded projects implemented by DILG and its attached agencies, and the submission of regular quarterly (for loan projects) and semestral reports (for grant projects) progress reports
AFIS II | AFIS II Project to complete the remaining deliverables under the project
All projects | DILG to monitor not only project outputs but also project outcomes and ensure project sustainability
Department of Energy (DOE)
PEEP | Submit Project Completion Report to include lessons learned and report on outcomes Ensure sustainability of the project; and Monitor/Report the outcomes of the project especially now that the project is already completed
E-TRIKE | Adhere to the procurement timeliness to avoid implementation delay Pro-active M&E activities to track the project activities and report issues for immediate action by DOE management
DOE | Full operationalization of the Program and Project Management Information System
Department of Science and Technology (DOST)
Improvement of the Flood Forecasting and Warning System for Magat Dam and Downstream | For the Improvement of the Flood Forecasting and Warning System for Magat Dam and Downstream, to start with the bidding process for the procurement of the project’s components
All projects | DOST and attached agencies to submit regular reports (i.e. semestral reporting for grants versus quarterly for loans reporting) of their ongoing grant-assisted projects’ accomplishments
Department of Communication and Transportation (DOTC)
CNS/ATM | On CNS/ATM Project, with the resumption of works following 21 months of suspension, the DOTC/CAAP is enjoined to exert maximum effort to ensure project completion within the revised loan validity period in order to finally realize the long delayed project benefits accruing from an upgraded CNS/ATM Systems
LADP | On Laguindingan Airport, DOTC-CAAP to come up with a revised and more realistic implementation plan for the installation of the needed ANS support facilities and equipment. Strict adherence to the said plan is critical to immediately address concerns on air transport passenger safety in the newly operated airport
GMA Ports | On GMA Ports Project, once BNP Paribas’ approval is secured relative to the proposed substitute project (Philippine Port and Coast Guard Capability Development Project), DOTC/PCG should fast-track finalization and implementation of the amended contract
CEMTS, NBAC-SEP, PPADP and MSCIP | On other DOTC projects (i.e., CEMTS, NBAC-SEP, PPADP and MSCIP), DOTC to exert best efforts to comply with conditions precedent to loan effectiveness and/or to accelerate the bidding process for consulting services and/or civil works
Batangas Port | On the completed Batangas Port, for DOTC/PPA to submit the materials relative to Roadmap to Decongest Manila and Divert Container Traffic to Batangas and Subic Ports to the Office of Cabinet Secretary for appropriate policy, as instructed by the INFRACOM
Department of Public Works and Highways (DPWH)
BC/RP | For BC/RP, with the DPWH decision to revert to the use of ODA financing as originally planned and as approved by the NEDA Board, to work for the early finalization of the MOU with the Government of Spain relative to the supplemental loan for the turn-key construction of 43 of the 91 already supplied bridges | March 2014 | DPWH/Special Bridges PMO (in close coordination with DOF)
BSAAR | For BSAAR, with the most recent ICC-TB endorsement for ICC-CC approval of the requested loan extension and the impending loan closing on 31 March 2013: • to make representations with KEDCF to facilitate processing and approval of the one-year loan extension; and • to submit a proposal on BSAAR II for ICC approval within the approved loan extension period. Henceforth, ICC-prescribed timelines for submission of requests for project changes should be faithfully observed | March 2014 2014 | DOF DPWH/KEDCF-PMO
RIIDP | For RIIDP, to immediately attend to actions required so as to start ICC approval process of the long-delayed request for project re-configuration | April 2014 | DPWH/ADB-PMO
POPSTIRP | For POPSTIRP, to expedite completion of works that remained uncompleted at loan closing in September 2013. Thereafter, to submit a project completion report to contain, among others, project outcomes and impacts, towards establishing that the project objectives were indeed achieved | 2014 | DPWH/BOD
GSO II | For GSO II, to implement the project and resolve all issues causing implementation delay with the view to completing the project within the extended loan validity period and in accordance with the agreed Catch-up Construction Schedule | 2014 - 2015 | DPWH PMO
All completed projects | For all completed projects, to submit a project completion report to contain, among others, project outcomes and impacts, towards establishing that the objectives of the projects were indeed achieved. Of special interest is the IDF grant for Philippines Institutionalizing Results Monitoring in DPWH, given the low compliance of PMOs in reporting project outcomes. For projects with closed loans but with uncompleted works, to continue reporting on project components being implemented using local funds until completion | 2014 | DPWH/PMOs and Planning Service
Cost overruns | On cost overruns, to report on impact of the cost control and monitoring system (e.g., Transport Cost Estimation System) that was undertaken under NRIMP relative to the current DPWH ODA Portfolio | 2014 | DPWH/ Planning Service
Inconsistency of ICC-approved cost with loan agreement cost | On inconsistency of ICC-approved cost with loan agreement cost, to adhere to ICC Guidelines which require ICC re-evaluation/notation of proposed projects that incur cost changes following the appraisal by the development partner | continuing | ICC Secretariat
Department of Social Welfare and Development (DSWD)
KC-AF & KC-MCC / Completed structures but damaged during the recent calamities that hit the country | Continue repair and rehabilitation efforts for calamity-damaged structures |  | KC-Project Management Office, Field Offices, concerned LGUs, WB and MCC
SPSP & SWDRP / For further utilization of the database and more appropriate project design and beneficiary identification of future programs/projects | For further utilization of the database and more appropriate project design and beneficiary identification of future programs/projects |  | NPMO, NHTO
4Ps (CCT) Program, SWDRP, SPSP / To measure the Program’s actual impact on target major outputs and to assess sustainability | (1) Conduct of future Impact Evaluation studies (Note: The second wave of impact evaluation studies commenced in November 2013. Results are expected for release in Sept. 2014.), (2) All RCT and RD areas to complete their data gathering |  | NPMO, NHTO, NSCB, may also involve other government units
CCT / For the benefit of disaster-affected individuals | DSWD will include in the regular CCT families affected by recent calamities |  | NPMO
(NHTS-PR) | Conduct of the 2nd round assessment |  | NPMO, NHTO, LGUs
Landbank of the Philippines (LBP)
CLEECP | LBP to finalize the proposal for restructuring of the project (i.e. further extension of the loan closing date and possible change in scope and design) for ICC approval | April 2014
SSLDIP | Given LBP’s proposal to focus on the areas affected by the recent calamities, LBP should come up with a realistic plan in marketing the facility to the calamity areas. Also, propose a streamline process in terms of sub loan approval, procurement, and others Follow-up with World Bank the status of additional two-year loan extension, as endorsed by DOF | Second quarter 2014
LBP | With the lower market lending rates, LBP should identify other possible projects that can be financed through ODA, e.g. propose expansion of scope of works Continue the conduct of orientation and briefing to all project stakeholders on the project objectives and requirements of the Development Partners to ensure continued support to the projects Negotiate with DOF on the reduction of FOREX and guarantee fess charges to make ODA facilities more attractive Document/Report the outcomes of completed projects/sub-projects
Local Water Utilities Administration (LWUA)
ICC-Cabinet Committee requirement | Performance Evaluation at the end of first year of extension period |  | LWUA-PMO
NEDA-MES
Last quarter (CY 2014)
Project Management, Supervi-sion, Administration, Coordina-tion and Operations Control | Strengthen the Project Management Unit. Reinforce the present PMU by adding officers and staff. The new team will be composed of: • Project Director: The Deputy Administrator for Area Operations • Project Manager: At least a Division Manager level • Action Officer for Luzon: A senior engineer with experience on WS project implementation and Contract Management • Action Officer for Bicol and Visayas: A senior engineer with experience on WS implementation and Contract Management |  | LWUA management First quarter of 2014
The contract for consulting services will expire in June 2014. Extension of the contract of the consultant may require a redefinition of the TOR and outputs as well as schedule and pay during the extension period | LWUA should revise/amend Consulting Services Contract to maximize the outputs of the Consultant in consideration of the loan extension period and costs implications |  | LWUA, Consultant, KfW Third quarter 2014.
WD’s capacity to pay timely monthly amortizations | LWUA to monitor closely the development of the WDs after the project. The advisory and training services of LWUA will be readily available. LWUA may exercise “take over rights” on WDs that fail to repay on the sub-loan on time |  | LWUA CY 2016 and beyond.
Metropolitan Waterworks and Sewerage System (MWSS)
Complementing the gains accruing from the AWUAIP-II and further ensuring water security in Metro Manila | ICC Processing of the following projects identified in the Water Security Legacy (WSL) Roadmap: (a) New Centennial Water Source Project-Construction of Multi-Purpose Dams; (b) Bulacan Bulk Water Project; and (c) BNAQIP |  | EPMD with inputs from the Concessionaires, NEDA Secretariat, and possibly the PPP Center of the Philippines (Since these Projects are currently proposed for implementation under the PPP scheme)
Complementing the gains accruing from the AWUAIP-II and further ensuring water security in Metro Manila | Completion of procurement of the following projects identified in the WSL: (a) ROM; and (b) ADDSP |  | EPMD
Long gestating water projects due to use of obsolete technologies that are wasteful, tedious and cumbersome to employ. | Application of new technologies used in AWUAIP-2 to the water supply projects in the WSL |  | PMO
Frequent turnover of skilled personnel; Lack of skilled manpower in the dept. | Training and provision of state-of-the art equipment for new personnel of MWSS on the use and application of these technologies |  | Training team composed of the most experienced and seasoned members of the PMO
Lack of awareness on the availability and use of new technologies in undertaking water supply projects | Conduct echo trainings/seminars in selected water districts and or public forum on the availability and usage of such technology(ies) |  | Training team composed of the most experienced and seasoned members of the PMO
National Irrigation Administration (NIA)
ARIIP | Prepare and provide Project Completion Report to concerned agencies i.e. NEDA | ASAP | NIA
HCAAP | Fast-track implementation/completion of remaining works under GPH funds | ASAP | DA/NIA
PIDP | Prepare and submit ICC-requisite documents to NEDA for evaluation of project restructuring proposal | ASAP/not later than 30 September 2014 | NIA
PIDP | Fast-track implementation of Civil Works component | ASAP | NIA
NISRIP | Expedite the conduct of Detailed Engineering Design | ASAP/should be completed by 3rd quarter 2014 to enable procurement of civil works contracts | NIA
Office of the Presidential Adviser on the Peace Process (OPAPP)
Participation in PIO meetings | For OPAPP to participate in quarterly Project Implementation Officers’ Meetings in order to benefit from the pool of expertise and the platform for discussion of implementation issues offered by such meetings |  | OPAPP
Familiarity with the sector | For NEDA-MES to learn more about the sector to gain a better appreciation of the activities, outputs, and outcomes of the sector’s projects which are not as straightforward as those of the other sectors |  | NEDA-MES
Supreme Court (SC)
JUSTICE Project: e-Courts / Absence of some of the technical specifications required from the system | SC to ensure that the missing technical specifications are in place prior to the Project’s roll-out to other sites |  | SC-PMO, Pilot Courts, MISO,CCL
JUSTICE Project: e-Courts / Lacking functionalities identified during the system design | Missing functionalities should be incorporated in e-Courts prior to roll-out |  | SC-PMO, Pilot Courts, MISO,CCL
JUSTICE Project: HUSTISYEAH / Difficulty in securing the cooperation of judges, court personnel, and prosecutors | Continuous dialogues during implementation and engagement of stakeholders in dialogues for future project sites |  | SC-PMO, Pilot Courts, MISO, OCA, PIO
JUSTICE Project: HUSTISYEAH / Need to be able to gather sufficient and reliable M&E data from case and docket records on time | Conduct appropriate M&E training for clerks of court and branch clerks |  | SC-PMO, Pilot Courts, MISO,OAS