## 4-B
Annex 4-B
CY 2014 ODA Portfolio Review
Lessons Learned
Category | Project Title/IA | Situation | Lessons Learned
I. Agriculture, Agrarian Reform and Natural Resources
Coordination with Stakeholders/ Implementing Partners/ Development Partners | Agrarian Reform Infrastructure Communities Phase III (DAR) | One of the causes of delay of the implementation of the project is additional legal and documentary requirements which have not been agreed upon during the inception of the Project. | It is deemed more beneficial for future projects to include provisions in the loan document that will ensure that documentary requirements agreed upon shall not be subject to changes in policy directions.
PMO Manpower/Capacity | Rapid Food Productivity Enhancement Program (DA) | At the start of the of the program, DA staff from various divisions were assigned (on ad hoc basis) to the PCO (spell out) | A PCO with staff working full time should be established prior to project implementation.
Project Design/Scope | Philippine Rural Development Program (DA) | DA's old practice of “top to bottom” business practices in the past have caused numerous failures in project implementation. Institutional reforms in re-orienting the sectoral planning process is therefore very essential to ensure successful delivery of various projects and programs. Infrastructural and technological interventions needed to underpin the transformation of the agriculture sector's large number of small-scale producers to become more market-oriented and vertically-integrated with agri-business are similarly very important. PRDP has been designed generally to support such improvements to successfully operationalize the decentralization reform agenda for the agricultural and fisheries sector. | MRDP provided a number of lessons that were adopted in the PRDP project design such as: (ii) institutional reforms in re-orienting the sectoral planning process (from top-to bottom to bottom-to-top) more likely to be effective if the benefits have already been established through operational efficiencies, rather than imposed from the top; (iii) the mandates of participating technical agencies need to be carefully observed and promoted through collaborative mechanisms, to ensure their sustained institutional support; (iv) local buy-in, ownership and sustainability is enhanced when interventions are implemented by LGUs, with agencies such as the DA providing “steering and technically-supportive” roles; and (v) networking among contiguous LGUs is critical for the effective management of natural resources.
| Environmental Development Program (DBP) | Philippine Water Revolving Fund (PWRF) requires specific co-financing arrangement which limits development efforts in the water sector. | Administration of the PWRF should allow some flexibility in its co-financing arrangement to encourage more development interventions in the water sector.
| Rapid Food Productivity Enhancement Program (DA) | In the original design of the farmers’ field school (FFS) under the project, the curriculum was set for one season. However, during one of the missions conducted by the DPs, it was found out that the duration might not be adequate to monitor the progress of farmers. | Duration of the FFS should cover at least two cropping seasons to also allow extension workers to monitor farming activities, and even recommend ways to improve production.
| Rapid Food Productivity Enhancement Program (DA) | In implementing RaFPEP that has wide area coverage, there were differences in various demographic profiles such as yield, production, hectarage, and cropping seasons per region. These differences were not addressed with the original implementing guidelines, specifically in the case of RaSSFiP. | Demographic profiles such as yield, production, hectarage, and cropping seasons per region should be considered in the national implementing guidelines of the project, so that partner regions can adjust to the seed distribution mode that will be more advantageous to the farmer beneficiaries.
Sustainability/O&M | Rapid Food Productivity Enhancement Program (DA) | With a lot of programs supporting farmers, there are cases wherein some interventions were put to waste. Therefore, with RaFPEP implementation, a cost-sharing scheme with the farmer beneficiaries was adopted resulting in an increased sense of ownership and participation to government interventions. | Through the cost-sharing scheme, the farmers were more responsible in planting the seeds which they have paid half the price (50 percent subsidy). For the CIS rehabilitation, it is more likely that FBs would efficiently manage the CISs when these are turned over to them.
II. Industry and Services
Knowledge Management | Trade Related Technical Assistance Project (DTI) | In the progress of implementation of the OPE 1, the substantial outputs and findings of the different components were not being shared and utilized at their maximum for the achievement of the Project's overall objectives. | Knowledge sharing of project outcomes Complementation and synergies.
III. Infrastructure Development
Budget and Funds Flow | Logistics Infrastructure Development Project (DBP) | By the end of 2009, the interest regime rendered ODA interest rates, in general, to be uncompetitive due to the fixed costs covering Foreign Exchange and Sovereign Guarantee Fees. (LIDP, EDP) | The low interest rate regime limit the ODA relending facility to projects requiring long term financing. Due to the high fixed costs charged by DOF to GFIs to cover Foreign Exchange and Sovereign Guarantee Fees, the pass on rate would be uncompetitive relative to commercial rates considering the low interest regime which began by the end of 2009.
Coordination with Stakeholders/ Implementing Partners/ Development Partners | Regional Infrastructure for Growth Project (DBP) | During project design phase, the SLA was assumed to be acceptable to both WB and DBP. However, during project implementation that WB insisted an SLA acceptable to them. GFI complied with the requirements of WB, however, the SLA is still pending WB approval up to the time the project was proposed to be restructured. | Approved SLA should be made a pre-requisite to loan signing with the DP so as not to delay project implementation and minimize result to potential project fall outs.
Peace and Order | Road Upgrading and Preservation Project (DPWH) | Some contractors experienced the burning of their equipment by the left-leaning groups due to non-payment of revolutionary tax, thus, rendering delay in the completion of the project. | Prior to implementation, DPWH to make representation with the DND for the security of the project area.
Procurement | Laguindingan Airport Development Project (DOTC) | Delay in the project completion due to separation of the two (2) project components namely: (1) Civil and Building Works; and (2) Air Navigation System and Support Facilities. | For airport development projects, it is best that the Air Navigation System and Support Facilities component be packaged with the Civil & Building works Components during procurement and implemented simultaneously in order to synchronize completion dates and ensure airport functionality upon completion.
Project Design/Scope | Logistics Infrastructure Development Project (DBP) | LIDP was originally designed to cover a broader range of infrastructure projects. However, transport & logistics under the propose ILAF approved by NEDA CabCom in 2005. Program designs was later revised by JICA mission in 2009 to focus on SRNH which was strongly identified with the previous Admin & given less emphasis during the incumbent Admin | Design of project should be broad and flexible as possible to adapt to changing market conditions
| Road Improvement and Institutional Development Project (DPWH) | The increase in cost was due to additional quantities, scope of works and changes in the design occurred during the As-Staked survey. Sometimes the quantities will be doubled once there is a delay in the implementation most especially if the road section was designed 3 or 5 years prior to implementation. The asphalt pavement is dynamic, hence, easy to deteriorate. | Update the design prior to implementation of the project if designed 3 or 5 years prior to implementation. The Design Consultants shall apply the principles of Value Engineering through its multi-disciplined team to ensure the quality of design, foster innovation, eliminate unnecessary and costly design elements without sacrificing safety and necessary quality. The gap between the detailed engineering design and implementation of the project should not exceed two (2) years in order to avoid substantial changes on the actual road condition which causes of variation orders, hence, increase in cost and will require extension of time.
Right-of-Way | Pinatubo Hazard Urgent Mitigation Project Phase III (DPWH) | Unacquired properties for project ROW, resulting in deletion of works on the problematic section or delay in the implementation. | Before project implementation, ROW must already been acquired.
| National Roads Improvement and Management Program Phase II (DPWH) | Road Right of Way and the relocation of utilities constituted the main issues and problems encountered in the implementation of the project | Settlement of all road right of way prior to the implementation of the project. Determining the location of utilities/facilities such as water, electrical and communication lines before and after detailed engineering stage. All respective owners of the said utilities shall be properly informed. The gap between the detailed engineering design of the project and its implementation should not exceed two (2) years to avoid substantial changes on the site condition which are causes of variation orders.
IV. Social Reform and Community Development
Budget/Funds Flow | KC-JFPR (DSWD) | Project agreement was signed in Mar 2014 but the imprest fund was only downloaded to DSWD in Oct 2014 as the funds had to be channeled through DOF (as the executing agency) and DBM. | Funds flow of grants may be fast tracked by transferring the funds directly to the implementing agency, not through the executing agency.
Coordination with Stakeholders/ Implementing Partners/ Development Partners | KC Millennium Challenge Corporation (DSWD) | Serious emphasis given to convergence by DSWD | Convergence of various DSWD programs facilitates efficient delivery of social services to the community.
Human Resource | KC Millennium Challenge Corporation (DSWD) | Recognition of occupational risks field staff are exposed to | Provision of additional staff benefits such as accident insurance
PMO Capacity/Manpower | KC-JFPR (DSWD) | Due to delays in downloading of funds, there was a change in staff recruitment arragnement. Hiring became the responsibility of ADB, not DSWD. Due to ADB’s hiring processes and policies, only 6 of 18 staff were hired from Aug to Dec 2014. | Guidelines, standards and process of hiring vary. In the context of projects that support emergency response/rehabilitation, assessing first which hiring process is faster and better should be done before transferring the responsibility to the development partner.
| KC Millennium Challenge Corporation (DSWD) | Sub-projects (SPs) will not always be completed within the established timetable | There are factors that may delay completion such as, but not limited to, remoteness of SP site, difficulties in getting the materials on site, weather conditions and availability of materials and labor especially in a calamity situation and peace & order situation. Notwithstanding, constant oversight and monitoring are necessary.
Sustainability/O&M | KC Millennium Challenge Corporation (DSWD) | The institutionalization of community organizations that would operate and manage SPs such as water systems and other common service facilities is not given its due emphasis in the project design. | The responsiveness, full functionality and long term sustainability of a SP should be the primary determinants in the design and development of the SP. For example, vertical SPs (i.e. Health Stations, Day Care Centers and School Buildings) should include water supply. Water system SPs should incorporate the organization and strengthening of water associations.
| KC Millennium Challenge Corporation (DSWD) | Although the quality of KC SPs is generally good that they can withstand calamities, there will always be a small percentage that will sustain damages and have their full functionality compromised. | Efficient implementation of SPs and linkaging with other stakeholders normally results in savings that will come in handy as a source for rehabilitation funds. There should always be a budget allowance that can be utilized for the rehabilitation of SPs damaged by calamities.