## 7B
Annex 7-B
CY 2014 ODA Portfolio Review
Recommendations for CY 2015 and Beyond for Implementing Agencies
Project / Issues | Recommendation / Action Plan | Timelines | Responsibility Center
Bureau of Internal Revenue (BIR)
NPSTAR | Document lessons learned on the implementation of NPSTAR | Immediate | BIR - PMIS
| Consider conduct of ex-post evaluation of NPSTAR | Within 2015 | BIR - PMIS
| Prepare Program Completion Report (PCR) | Immediate | BIR – PMIS & WB
RARP / Monitoring and evaluation; Reporting on progress | Report on the implementation issues of the RARP | Quarterly | BIR/ DOF & RIPS
RARP / Project Implementation | Fast-track RARP implementation considering a wide gap of elapsed time vis-à-vis financial disbursements | Immediate | BIR/ DOF & RIPS
Department of Agriculture (DA)
CHARMP 2/ OFID | Stricter implementation of the action plan with milestones/check-points against which critical actions should be undertaken, e.g., discontinue slow moving activity given the less than one year implementation period available | Immediate | DA
All projects | On sustainability issues, there should be continuous coaching and monitoring of beneficiaries given their vulnerabilities to major economic shocks as in the case of RaFPEP and RPC. | Immediate | DA
All projects | Develop/institute measures to minimize the impact of the change in administration at the national and local levels in 2016 | Immediate | DA
Department of Agrarian Reform (DAR)
ARCP II | Fast track implementation particularly under OFID loan | December 2015 | DAR
ARISP III | Fast track implementation of subprojects | December 2016 | DAR
IARCDSP | Amendments on the MOU between Government of Italy and Philippines | 2nd Quarter 2015 | DAR
MinSAAD | Hiring of Consultants for the project review | Immediate | DAR
TPKP | Follow up status of the suspension of construction of bridges (Senate Blue Ribbon Committee) | Immediate | DAR
Development Bank of the Philippines (DBP)
LIDP | Continuous marketing of LIDP to its expanded target sub-borrowers | Continuing | DBP
| Report on the improved performance of the credit facility arising from the expanded list of eligible subprojects | June 2015 | DBP
EDP | Consider extension of loan validity to ensure availability of funding beyond loan closing | Ongoing | DBP
| Close monitoring of sub-loan approval and releases | Continuing | DBP
| Monitoring of outcomes/results of implementation of sub-projects | Continuing | DBP
All Projects | Continue to proactively market the facilities to potential client sand closely monitor approved accounts to expedite disbursement | Continuing | DBP
| Monitor/Document initial results/outcomes of completed subprojects | Continuing | DBP
| Continue dialogue with the DOF regarding reduction on FOREX and guarantee fees | Continuing | DBP
| Continue to proactively market the facilities to potential client sand closely monitor approved accounts to expedite disbursement | Continuing | DBP
| Monitor/Document initial results/outcomes of completed subprojects | Continuing | DBP
| Continue dialogue with the DOF regarding reduction on FOREX and guarantee fees | Continuing | DBP
| DBP to consider inclusion in the sub-loan agreement between DBP and sub-borrower the responsibility of the borrower to keep track and report to DBP achievements on O&E indicators indicated in the logical framework/Key Results Areas (KRAs) | Continuing | DBP
Department of Environment and Natural Resources (DENR)
ICRMP | Prepare and provide Project Completion Report to concerned agencies i.e. NEDA | Immediate | DENR
FMP | Institute catch-up plan to expedite implementation | Immediate | DENR
INREMP | Ascertain the feasibility of absorbing the unutilized US$10 million portion of DA for CAR components (CHARMP2)and the implications it may bring to the project e.g. project restructuring, etc. | 2015 | DENR/DA
CBFMMP | Convene necessary M&E Team/s to cover all M&E requests (validation) from the LGUs to facilitate payment of completed activities | Immediate/2015 | DENR
| Continuous guidance/assistance to LGUs to enable fast tracking of submissions of progress billings and List of Expenditures (LOEs) | 2015 | DENR
All projects | Provision of adequate organic personnel complement to the implementing units and continued capability building to strengthen project management capacities. | 2015 and beyond | DENR
| Institute measure/s to mitigate impact to projects of the upcoming 2016 elections e.g. projects with LGU participation | 2015-2016 | DENR
Department of Education (DepEd)
BEAM-ARMM | Submit requirements for BEAM-ARMM | 6 May 2015 | DepEd
EQuALLS 2, and LCDisability | Submit PCR for EQuALLS 2, and LCDisability | June 2015 | DepEd
LIPAD | Prepare PCR for LIPAD | August 2015 | DepEd
All Projects | Improve reporting on projects | July 2015 | DepEd
| Start taking stock of good practices for GPA 2016 | December 2015 | DepEd
Department of Interior and Local Government (DILG)
BFP Capability Building Program for Selected Priority Cities Project | DILG to ensure that the beneficiary cities have the capacity to maintain the fire trucks provided |  | DILG
All projects | Semestral reporting of the progress of implementation of DILG-implemented grants should be provided to the NEDA-MES. |  | DILG
| For the 2nd phase of the project, DILG to actively monitor progress of project implementation particularly on financial performance. |  | DILG
Department of Energy (DOE)
E-TRIKE | Adhere to the revised procurement timelines to avoid further implementation delays. | 2015 | DOE
| Prepare catch-up plan to make up for incurred delays in the first year of implementation, including a set of strategies to create demand for the E-trikes | 2015 | DOE
| Improve disbursement target setting in 2015, taking into account the effect of the delays in bidding out E-trike units on financial disbursements | 1st Quarter 2015 | DOE
| If difficulties in the deployment of E-trike units continues to persist after two years of project implementation, consider ICC-reevaluation for project restructuring. | 2017 | DOE
PEEP | Continue tracking the progress of results/outcome indicators of PEEP. |  | DOE
All Projects | More pro-active M&E activities for ongoing projects to track activities and report issues for immediate action by DOE management. | 2015 and beyond | DOE
| Submission of regular updates to MES | 2015 | DOE
Department of Science and Technology (DOST)
Project for Improvement of the Meteorological Radar | Submit Project Completion Report | June 2015 | DOST
Enhancement of Earthquake and Volcano Monitoring and Effective Utilization of Disaster Mitigation Information in the Philippines | Ensure completion/delivery of all project activities. | February 2015 | DOST
| Submit Project Completion Report | August 2015 | DOST
Grant Aid for the Project for Improvement of Equipment for Disaster Risk Management | Ensure completion/delivery of all project activities | December 2015 | DOST
Establishment of Communications, Ocean & Meteorological Satellite Data Analysis System in the Philippines. | Ensure completion/delivery of all project activities | December 2016 | DOST
All projects | DOST and attached agencies to submit regular reports (i.e. semestral reporting for grants versus quarterly for loans reporting) of their ongoing projects’ accomplishments | June and December 2015 | DOST
| DOST and attached agencies to monitor not only project outputs but also project outcomes and ensure sustainability of its completed projects |  | DOST
Department of Communication and Transportation (DOTC)
CNS-ATM | Location of the last surveillance radar (i.e. Pasuquin, Ilocos Norte or Laoag Airport) must be decided/secured as soon as possible to complete the implementation of the project in accordance with the revised schedule. | March 2015 | DOTC
All projects | DOTC to accomplish the targets under financial and physical dimensions of projects to improve performance and adhere to procurement timelines to start actual implementation of projects | 2015 | DOTC
| Concerned PMUs to submit to NEDA-MES relevant project information (e.g. physical andfinancial targets, description, objectives, etc.) on or before 30 May 2015 | 30 May 2015 | DOTC
| Regular submission of progress reports | Continuing | DOTC
Department of Public Works and Highways (DPWH)
NRIMP | Expedite finalization of the design of Year 4 works and procurement of Year 3 and 4 works under Preventive Maintenance | March 2016 | DPWH/UPMO-RMC2
| Facilitate procurement of contracts relative to TA to LGUs | 2nd Quarter 2015 | DPWH/UPMO-RMC2
| Expedite decision on the variation orders related to design changes in RI and LTPBM contracts to speed up disbursement of project funds | 2nd Quarter 2015 | DPWH/UPMO-RMC2
BC/RP | Finalize resolution endorsing Supply Contract to DOF to secure the supplemental loan from the Government of Spain | March 2015 | DPWH/UPMO- BMC
GSO | Utilize more effective means of resolving all issues causing implementation delays | 1st Quarter 2015 | DPWH UPMO-RMC2
PHUMP III and PMRCIP II | Ensure sustainability by reconfirming plans for operation and maintenance (O&M) of outputs, with focus on specific budget measures and distribution of roles and responsibilities | 2015 | DPWH UPMO-FCMC
ARBP II, RUPP, CLLEX, SPCRP, FRIMP and IDRRCCAM | Expedite procurement of civil works/consulting services contracts | 2015 | DPWH UPMO-RMC1 and FCMC
All projects | Improve disbursement target setting. | February 2015 | DPWH/UPMOs
| Ensure consistency of figures submitted to DPs and NEDA | February 2016 | DPWH/UPMOs
Department of Social Welfare and Development (DSWD)
KALAHI-CIDSS-MCC | Install mechanisms that would enhance a SP’s sustainability O&M | Immediate | KC-NPMO, RPMO, and MCC
| Develop alternative measures to compensate staff shortage in the event that ACTs/MCTs were unable to be hired | 2nd Quarter 2015 | KC-NPMO, RPMO, MCC
KALAHI-CIDSS-NCDDP | Complete hiring of required field staff | June 2015 | NPMO
| Provide further technical support to inexperienced ACTs | Immediate | NPMO, TAU
KALAHI-CIDDSC-AF | Sharing of Project Completion Report | Immediate | NPMO, WB
UNFPA 7th Country Programme | Mobilize resources to fund the roll-out of trainings end establish Brgy. VAW Desks officers | June 2015 | TAU
Department of Trade and Industry (DTI)
RUMEPP | An exit and transitory strategy to be developed, particularly to institutionalize support to DTI provincial offices. | 2015 | DTI/SBC
| To continuously support MEs and other beneficiaries of RuMEPP thru its accredited MFIs until 2016 | 2015 to 2016 | SBC
| DTI to ensure availability of necessary funding to support BDS for MEs to ensure program sustainability | 2015 to 2016 | DTI/SBC
| Completion of the impact evaluation study of the RuMEPP in 2015 and share findings with concerned agencies | Within 2015 | IFAD
All projects | Study the viability of mainstreaming the program’s approach in DTI’s regular program | 2015 to 2016 | DTI/SBC
Land Bank of the Philippines (LBP)
MWMP | Fast track procurement of the sewer network (Manila Water) and design and construction of STPs (Maynilad) | June 2015 | LBP
SSLDIP | Coordinate with DOF and DBM on the finalization of MOA on the fund transfer of the 90 percent grant from the National Government. | Immediate | LBP/NEDA-MES
| Ensure inclusion of the project in the agenda on the next NEDA Board meeting | Immediate | LBP/NEDA-MES
ACSP | Consider loan extension given the remaining 1.5 implementation period and 60% utilization as of December 2014 | August 2015 | LBP
CBFMP | LBP to ensure completion of project activities as the sub-loan is already fully utilized. |  | LBP
CLEECP | LBP to secure an official/final communication from KfW on the closing of the loan |  | LBP
Yolanda Reconstruction Program | Fast track evaluation of proposals submitted by LGUs. | June 2015 and December 2015 | LBP
| Assist LGUs in complying with the documentary requirements to facilitate release of funds. | June 2015 and December 2015 | LB
| Regular submission of progress report to NEDA. | June 2015 and December 2015 | LB
| LBP to require the LGUs to document initial results/outcomes of the project intervention | June 2015 and December 2015 | LB
Future LBP Projects | LBP to consider inclusion in the sub-loan agreement between LBP and sub-borrower the responsibility of the borrower to keep track and report to LBP achievements on O&E indicators indicated in the logical framework/Key Results Areas (KRAs) |  | LBP
Local Water Utilities Administration (LWUA)
PTWSSP-III | Shorten the pre-qualification/pre-approval process of the remaining water supply proposals and ensure strict implementation of timelines |  | LWUA-PMO
PTWSSP-III | Reinforce the present PMU by adding officers and staff. | 1st Quarter 2015 | LWUA management
PTWSSP-III | Overhaul and accelerate procurement activities to only 2 months (max) and conduct bidding of cluster proposals simultaneously | CY 2016 and beyond | LWUA
PTWSSP-III | PMO to decide whether to request for extension of loan validity or to continue the project using LWUA’s funds. | CY 2016 and beyond | LWUA
National Irrigation Administration (NIA)
JALAUR | Secure NEDA approval for possible implementation extension only in the last year of implementation |  | NIA
PIDP | Catch up in the ongoing civil works activities | Immediate | NIA
| Closely monitor civil works construction until its completion | Immediate | NEDA
| NIA to address issues/concerns raised during the 19 May 2015 NEDA Board Meeting | Before next NEDA Board Meeting | NIA
Office of the Presidential Adviser on the Peace Process (OPAPP)
Monitoring & Communicating Results: Capacity-Building for the Office of the Presidential Adviser on the Peace Process | Submit Project Completion Report | April 2015 | OPAPP
| Ensure completion/delivery of all project activities. |  | OPAPP
| Submit Project Completion Report | September 2015 | OPAPP
OPAPP-Department of Foreign Affairs and Trade (DFAT) Australia Technical Assistance Facility (TAF) in Support of the Government of the Philippines Peace, Security and Development Agenda | Ensure completion/delivery of all project activities | May 2015 | OPAPP
| Submit Project Completion Report | November 2015 | OPAPP
All Projects | OPAPP agencies to submit regular reports (i.e. semestral reporting for grants versus quarterly for loans reporting) of their ongoing projects’ accomplishments | June and December 2015 | OPAPP
| OPAPP to monitor not only project outputs but also project outcomes and ensure sustainability of its completed projects. |  | OPAPP