## Sample Form 3 - WFP
Program/Project Title: | Local Innovation Facilitators Training and Cascading Workshops
Agency/Department: | National Economic and Development Authority (NEDA)
Implementing Entity: | Central Office - Innovation Staff
Implementation Period: | January 2025 to December 2025
Proposed Budget: | 1386000
General Objective: | To promote innovation and capacitate local leaders with creative and design thinking that will be integral in pursuing innovative solutions to community problems
WORK PLAN |  |  |  | PHYSICAL OUTPUTS/ ACCOMPLISHMENT | [12 empty] | FINANCIAL TARGETS
Specific Objectives | Outcomes | Activity/ Physical Outputs | Output Indicator | Target | Timeline/ Gantt Chart | [11 empty] | Resource Requirement
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Line-Item Expense | Item/s Description | ESTIMATED COST
[5 empty] | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |  |  | UNIT ESTIMATE | QTY. | SUB-TOTAL
Specific Objective 1: To develop a pool of specialized Filipino trainers/ professionals/ practitioners who have both the knowledge and skills to develop and promote innovation and creative thinking in their respective fields and communities | Increase in the number of facilitators from 10 to 100 who can be tapped to help cascade and train others to develop and promote innovation and creative thinking | 1.1 Call for Applicants | No. of applications received | 20 | Q1 JAN: Call for Applicants; Q1 FEB: Call for Applicants | N/A | N/A | 0 | 0 | 0
|  | 1.2 Deliberation and Approval of Applicants | No. of applicants deliberated | 20 | Q1 FEB: Deliberation & Approval of Applicants; Q1 MAR: Deliberation & Approval of Applicants | Representation Expenses | Snacks and Lunch of Deliberation Panel and Secretariat | 3000 | 2 | 6000
|  | 1.3 Attendance to Local/Foreign Innovation & Design Thinking Facilitator Program | No. of delegates who successfully completed the facilitator program | 10 | Q2 APR: Conduct of Local/Foreign Innovation & Design Thinking Facilitator Program; Q2 MAY: Conduct of Local/Foreign Innovation & Design Thinking Facilitator Program; Q2 JUN: Conduct of Local/Foreign Innovation & Design Thinking Facilitator Program | Traveling Expenses - Local | Round-Trip Air/Land/Boat Fare for 10 pax | 15000 | 10 | 150000
[18 empty] | Accommodation for 30 days for 10 pax | 30000 | 10 | 300000
[18 empty] | Living Allowance for 30 days for 10 pax | 40000 | 10 | 400000
|  | 1.4 Implementation of Re-entry/Cascading Plan | No. of re-entry/cascading plans implemented | 10 | Q3 JUL: Start of Implementation of Re-entry/ Cascading Plans; Q3 AUG: Implementation of Re-entry/ Cascading Plans; Q3 SEP: End of Implementation of Re-entry/ Cascading Plans; Q4 NOV: Writing and Submission of Accomplishment Reports; Q4 DEC: Writing and Submission of Accomplishment Reports | N/A | N/A | 0 | 0 | 0
Specific Objective 2: To train and capacitate personnel in local development units with design thinking and innovation that can be applied in creating new solutions to their communities | Increase in the number of personnel in the local level who are skilled with design thinking and is pursuing innovative solutions to local challenges | 2.1 Procurement of Office and ICT Equipment and Project Supplies and Materials | No. of equipment, supplies and materials procured | 2 | Q1 MAR: Procurement of Project Supplies & Materials; Q2 APR: Procurement of Project Supplies & Materials; Q2 MAY: Procurement of Project Supplies & Materials | Office Supplies Expenses | Bond Paper, Toner Cartridge, Stapler, Staple Wire, Puncher, Pens, Folders, Envelopes, etc. | 30000 | 1 | 30000
[17 empty] | Semi-Expendable Information and Communications Technology Equipment | Laser Printer | 20000 | 1 | 20000
|  | 2.2 Field Work/Visits to Target Stakeholders | No. of activities conducted | 10 | Q3 AUG: 5 Field Work/Visits; Q4 OCT: 5 Field Work/Visits | Traveling Expenses - Local | Round-Trip Air/Land/Boat Fare for 10 pax | 1000 | 10 | 10000
[18 empty] | Accommodation for 5 days for 10 pax | 7000 | 10 | 70000
|  | 2.3 Conduct of Innovation and Design Thinking Workshop to Local Communities | No. of workshops conducted | 10 | Q3 AUG: 5 Field Work/Visits; Q4 OCT: 5 Field Workshops | Rent/ Lease Expenses | Rent/Lease of Venue | 15000 | 10 | 150000
[17 empty] | Representation Expenses | Snacks and Lunch for Participants | 25000 | 10 | 250000
[19 empty] | TOTAL |  | 1386000
Prepared by: |  | Certified by: |  | Approved by: | [12 empty] | Prepared by: |  | Certified by: |  |  | Approved by:
Name and Signature of Project Leader |  | Accountant/Budget/Finance Officer |  |  | Q1 JAN: Head of Agency | Name and Signature of Project Leader |  | Accountant/Budget/Finance Officer |  |  | Head of Agency